Program Management Office (PMO)

Project Management

Metrics Guidebook

Revision Date: February 23, 2001

Revision: 1.0

Product Code: GTA-PMO-GUI-002

Table of Contents

1.0  Introduction	1

1.1  Identification Of Document	1

1.2  Scope Of Document	1

1.3  Purpose Of Document	2

1.4  Document Organization	2

1.5  Guidelines For Using The Document	3

1.6  Guidelines For Updating This Document	3

2.0  Related Documentation	4

2.1  Parent Documents	4

2.2  Applicable Documents	5

2.3  Information Documents	5

3.0  Foundation	6

3.1  Terminology	7

3.2  Baselines	8

3.3  Metrics Library	10

3.4  Metrics Strategies for Small Projects	10

4.0  Metrics Process	11

4.1  Overview	11

4.2	Project Management Metrics	12

4.2.1  Cost Metrics	12

4.2.1.1  Cost (Planned vs. Actual)	13

4.2.1.2  Earned Value	14

4.2.1.3  Margin	15

4.2.1.4  Management Reserve Balance	16

4.2.2  Staffing Metrics	16

4.2.2.1  Staffing (Planned versus Actual)	17

4.2.2.2  Staffing Mix (Salary, Hourly, Contractual)	18

4.2.2.3  Effort (Planned VS. Actual)	19

4.2.3  Quality Metrics	20

4.2.3.1  Deliverables (On Time vs. Late)	20

4.2.3.2  Deliverables (Accepted vs. Rejected)	21

4.2.4  Schedule Metrics	22

4.2.4.1  Delivables (Total Number)	23

4.2.4.2  Deliverables (Complete/Remaining/Late)	24

4.2.4.3  Deliverables (Late/Aging)	25

4.2.5  Size Metrics	25

4.2.5.1  Function Points	26

4.2.5.2  Total Number of Requirements	27

4.2.6  Change Request Metrics (CR)	28

4.2.6.1  Status (Approved, Rejected, Pending)	28

4.2.6.2  Cost Impact	29

4.2.7  Risks Metrics	30

4.2.7.1  Risks	31

4.2.7.2  Action Items	35

4.2.7.3  Issues	38

5.0  Status Accounting	41

5.1  Reports	41

5.1.1  Weekly Status Meetings	41

5.1.2  Program Reviews	43

5.1.3  Formal Reviews	44

5.2  Checklists	46

6.0  Supporting Reviews and Audits	47

6.1  Reviews	47

6.2  Audits	47

List of Figures

Figure 1: Document Organization	1

Figure 2: Related Documentaiton-Section 2	4

Figure 3: Foundation	6

Figure 4: Components of Metrics Baseline	7

Figure 5: Metrics Process	11

Figure 6: Cost (Planned vs. Actual)	13

Figure 7: Earned Value Management	14

Figure 8: Margin	15

Figure 9: Management Reserve Balance	16

Figure 10: Staffing (Planned vs Actual)	17

Figure 11: Staffing Mix	18

Figure 12: Effort (Planned vs. Actual)	19

Figure 13: Deliverables (On Time vs. Late)	20

Figure 14: Deliverables (Accepted vs. Rejected)	21

Figure 15: Deliverables (Planned vs. Actual)	23

Figure 16: Deliverables (Complete/Remaining/Late)	24

Figure 17: Deliverables (Late/Aging)	25

Figure 18: Number of Function Points	26

Figure 19: Number of Requirements	27

Figure 20: Change Requests (Approved/Rejected/Pending)	28

Figure 21: Cost Impact (Change Request)	29

Figure 22: Number of Risks	31

Figure 23: Risks (Distribution)	32

Figure 24: Risk Aging	33

Figure 25: Number of Dollars at Risk	34

Figure 26: Number of Action Items	35

Figure 27: Action Items (Distribution)	36

Figure 28: Action Item Aging	37

Figure 29: Number of Issues	38

Figure 30: Issues (Distribution)	39

Figure 31: Issue Aging	40

Figure 32: Status Accounting	41

Figure 33: Supporting Reviews and Audits	47

List of Appendicies

None

Revision History

| Revision Number | Date | Comment |
| --- | --- | --- |
| 1.0 | February 23, 2001 | Original Scope |

# 1.0  Introduction

Figure 1: Document Organization

The following paragraphs provide reference to parent, applicable, and information documents relevant to Metrics Collection, Analysis, and Reporting. Figure 1 illustrates this section in the context of the entire guidebook.

## 1.1  Identification Of Document

This document is identified as the Metrics Guidebook, Product Code: GTA-PMO-GUI-002.

## 1.2  Scope Of Document

A.	This guidebook contains Project Management Metrics procedures to be followed by all projects in accordance with corporate policies and procedures.

B.	As referenced within this guidebook, metrics collection involves measuring specific items throughout the project life cycle from the perspective of project management metrics related to product quality and progress.

## 1.3  Purpose Of Document

- The purpose of this guidebook is to establish standard methods by which Metrics Collection, Reporting, and Analysis is accomplished.  These methods indicate responsibilities for the various aspects of metrics collection, reporting and analysis and indicate which aspects must be documented and reported via other procedures.

- Methods provided in this manual may be tailored for each program according to the Statement of Work (SOW), or Charter.  Tailoring of the methods may be performed in conjunction with the proposal generation and requires no tailoring.  The metrics strategy for individual projects will be reviewed by Quality Assurance (QA), Configuration Management (CM) and approved by the program/project manager(s) responsible for the proposed project.

- The output from this procedure may be used to provide graphical respresentations of project performance analysis in conjunction with reviews, presentations, reports, and executive level dashboards.

## 1.4  Document Organization

The guidebook is organized as follows:

| Section | Title | Description |
| --- | --- | --- |
| 1 | Introduction | Document identification, scope, purpose, volume organization, and guidelines for using and updating the guidebook. |
| 2 | Related Documentation | Parent documents, applicable documents, and information documents. |
| 3 | Foundation | Establishes the framework for metrics including basic terminology, baselines, categorization and content of metrics. |
| 4 | Metrics Process | Identifies Metrics process by activities within phases and defines specific metrics and responsibility. |
| 5 | Status Accounting | Identifies the type of reports that should be generated as well as checklists to determine if the appropriate measurements are being accomplished for a project. |
| 6 | Supporting Reviews and Audits | Contains hints and/or guidelines for successful reviews (project and subcontracts) and Audits. |

## 1.5  Guidelines For Using The Document

A.	The Metrics Guidebook methods provide standards for the technical, objective approach to metrics and measurement.  This methodology has evolved in a disciplined and controlled manner from Project Management practices that have been employed in a series of successful programs.

B.	The resulting practices, standards, and methods identified for the project will be amplified in the PMP created for each project.  Each  project will need to have an established metrics program.  Additionally, there will be an establish suite of metrics that will be consistent across all similar projects to faciliate comparitive performance assessment and executive level project performance reporting.

C.	The sections of this guidebook apply to all projects.  Information contained within the sections is not meant to duplicate information within the PMP but to be used in conjunction with the parent document which defines standards.

## 1.6  Guidelines For Updating This Document

This guidebook is intended to be a living document and will be maintained by the Georgia Technology Authority (GTA), Program Management Office (PMO) to continuously reflect the latest metrics and measurement practices.  Recommendations to update this guidebook should be forwarded to the PMO, using the PILL form, for disposition.  The PMO will review and approve changes before incorporation into this document.

# 2.0  Related Documentation

Figure 2: Related Documentaiton-Section 2

The following paragraphs provide reference to parent, applicable, and information documents relevant to Metrics Collection, Reporting, and Measurement. Figure 2 illustrates this section in context to the entire guidebook.

## 2.1  Parent Documents

The Organizations’ Policies are parents to this document:

| Title | Product Code |
| --- | --- |
| Project Planning Policy | GTA-PMO-POL-002 |
| Project Tracking and Oversight Policy | GTA-PMO-POL-003 |

## 2.2  Applicable Documents

A.	The following documents are referenced herein and are directly applicable to this document to the extent indicated within the text of this document.

B.	Internet standards are available in the Process Asset Library (PAL).  The standards may (optionally) be available through your department, division, agency, or the PMO.

C.	Internal standards are listed below.

| Document | Title |
| --- | --- |
| GTA-PMO-PRO-500 | Change Control |
| GTA-PMO-PRO-200 | Program Reviews |
| GTA-PMO-PRO-101 | PMP Development |
| GTA-PMO-PRO-102 | Schedule Development |

## 2.3  Information Documents

The following documents amplify or clarify the information presented in this document but are not binding.

| Document | Title |
| --- | --- |
| CMU/SEI-91-TR-24 ESD-TR-91-24 | Project Management Body of Knowledge Guidebook |

# 3.0  Foundation

Figure 3: Foundation

- Figure 3 illustrates the Foundation section in context to the entire guidebook.

- An essential element in any metrics program is to have a baseline containing “planned” results, along with supporting Basis of Estimates (BOEs) to support those planned results.  These baseline versions must not be lost during revisions of estimates when recording “actuals” and perhaps creating new planned versions.  All versions from the first to the last, along with supporting BOEs must be kept and archived historically beyond the project to better aid future estimation.  To accomplish this, Configuration Management (CM), Project Administration (PA), and Quality Assurance must be an integral part of project management processes across all phases of the life cycle.

Figure 4: Components of Metrics Baseline

- Metrics measurement and analysis functions are controlling disciplines enabling baselined projects to be maintained while actual results are measured.  The key requirement for success of a good metrics program is the joint commitment of all levels of management, and the project team, to enforce its use throughout the project lifetime.  Figure 4 graphically depicts key components to an effective metrics baseline.

- Often, projects that are experiencing difficulty, abandon their metrics program, as robust metrics provide maximum visibility into categorical status, issues, and progress.  Furthermore, metrics must be relevant both to the area in which it is focused, but also the level of the organization that will view that particular measure. Additionally, metrics measurement and reporting personnel must be cognizant of project management processes, and have attended the appropriate project management training courses.

## 3.1  Terminology

This paragraph contains an alphabetized sequence of Metrics Collection, Analysis, and Reporting  terminology explanations.

| Term | Description |
| --- | --- |
| Actual | The measured value of the metric at the time point in time taken |
| BCAC | Budgeted Cost at Completion – The budgeted cost for the project |
| BOE | Basis of Estimate |
| CM | Configuration Management |
| ECAC | Estimated Cost at Completion – The projected cost to complete the project |
| GTA | Georgia Technology Authority |
| Metric | An objective measurement of a physical, standard, temporal or financial entity |
| PA | Project Administrator |
| PC/A | Project Consultant/Analyst |
| Planned | The predicted value of the metric in question at the particular point in time it is measured. |
| PMO | Program Management Office |
| QA | Quality Assurance |
| Variance | The difference Between the planned metric value and the actual metric value |

## 3.2  Baselines

The following metrics are designated by category and product code for each baseline in the Project Life Cycle  Functional, Allocated, Product, and Special are baselines associated with the Software Development Life Cycle (SDLC).  Only Project Management metrics are listed in this docment, and are baselined at the Initial Requirements Review (IRR) along with the Project Management Plan (PMP).  The following designators are used to measure the status of each metric at each baseline:

1.	N = New Metric baseline.  The metric and its BOE data are baselined under formal configuration management control.

2.	NV - Next Version.  The metric is bench-checked for performance, and perhaps a new baseline is created.  If so, the original baseline data for the metric is still maintained, but a new baseline and its BOE data are baselined as a new formal version and progress then tracked against the new data.

| Metric | Category | Product Code | PM | Functional | Allocated | Product | Special |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cost (Planned Versus Actual) | Cost | GP-MET-001 | N | NV | NV | NV | N |
| Earned Value | Cost | GP-MET-002 | N | NV | NV | NV | N |
| Margin | Cost | GP-MET-003 | N | NV | NV | NV | N |
| Management Reserve Balance | Cost | GP-MET-004 | N | NV | NV | NV | N |
| Staffing (Planned Versus Actual) | Staffing | GP-MET-005 | N | NV | NV | NV | N |
| Staffing Mix | Staffing | GP-MET-006 | N | NV | NV | NV | N |
| Effort | Staffing | GP-MET-007 | N | NV | NV | NV | N |
| Deliverables (On Time Versus Late) | Quality | GP-MET-008 | N | NV | NV | NV | N |
| Deliverables (Accepted Versus Rejected) | Quality | GP-MET-009 | N | NV | NV | NV | N |
| Deliverables (Total Number) | Schedule | GP-MET-010 | N | NV | NV | NV | N |
| Deliverables (Complete/Remaining/ Late) | Schedule | GP-MET-011 | N | NV | NV | NV | N |
| Deliverables (Late/Aging) | Schedule | GP-MET-012 | N | NV | NV | NV | N |
| Function Point Size | Sizing | GP-MET-013 | N | NV | NV | NV | N |
| Total Number of Requirements | Sizing | GP-MET-014 | N | NV | NV | NV | N |
| CR Status (Approved, Rejected, Pending) | Change | GP-MET-015 | N | NV | NV | NV | N |
| Cost Impact | Change | GP-MET-016 | N | NV | NV | NV | N |
| CR Categorization (Cost, Schedule, Quality) | Change | GP-MET-017 | N | NV | NV | NV | N |
| Risk Items Open | Risk | GP-MET-018 | N | NV | NV | NV | N |
| Risk Item Distribution | Risk | GP-MET-019 | N | NV | NV | NV | N |
| Risk Aging | Risk | GP-MET-020 | N | NV | NV | NV | N |
| Risk Total Value | Risk | GP-MET-021 | N | NV | NV | NV | N |
| Issue Items Open | Risk | GP-MET-022 | N | NV | NV | NV | N |
| Issue Item Distribution | Risk | GP-MET-023 | N | NV | NV | NV | N |
| Issue Aging | Risk | GP-MET-024 | N | NV | NV | NV | N |
| Action Items Open | Risk | GP-MET-025 | N | NV | NV | NV | N |
| Action Item Item Distribution | Risk | GP-MET-026 | N | NV | NV | NV | N |
| Action Item Aging | Risk | GP-MET-027 | N | NV | NV | NV | N |

## 3.3  Metrics Library

Maintain all metrics (both past and previous versions) as well as all historical versions of the estimation data, including source of data, classifications of data, assumptions, constraints, and estimation methods that support such data.  These items should be version managed using the CM library tool for the project.

## 3.4  Metrics Strategies for Small Projects

Projects using abbreviated life cycles, or operations projects should benchmark the standard metrics contained in this guide and provide tailoring out for items that will not be beneficial.  For instance, function points for a four-week project may not be advantageous, as the project will complete before the first reporting period may arrive.  Consider, however, that projects that are fast moving (time constrained) and high risk, may require the same metrics, but reported more frequently.

# 4.0  Metrics Process

Figure 5: Metrics Process

## 4.1  Overview

A.	Metrics are collected for measuring the progress of a project against its planned budget, schedule, resource usage, and error rates, and of establishing a historical database which will aid in planning and forecasting future projects. Figure 5 illustrates the Metrics Process in relation to the other sections in this guidebook.

B.	Metrics are also used as an indication of model stability which signals the time to proceed into the next phase of the project life cycle.

C.	Metrics collected and reported for projects include the following six categories:

- Cost Metrics;

- Staffing Metrics;

- Quality Metrics;

- Schedule Metrics;

- Size Metrics; and

- Risk Metrics.

D.	The following sections summarize the areas for collecting and reporting metrics.

## Project Management Metrics

The following sections reflect the range of Project Management Metrics along with illustrations depicting how the data could be represented for reporting purposes.

### 4.2.1  Cost Metrics

Cost metrics are used throughout the project life cycle, and are included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Cost | IRR | PA | Cost (Planned vs. Actual) | Monthly | Program Reviews & Formal Reviews |
|  | IRR | PA | Earned Value | Monthly | Program Reviews & Formal Reviews |
|  | IRR | PA | Margin | Monthly | Program Reviews & Formal Reviews |
|  | IRR | PA | Management Reserve Balance | Monthly | Program Reviews & Formal Reviews |

#### 4.2.1.1  Cost (Planned vs. Actual)

The purpose of this metric is to measure how well the project costs are performing according to plan.  This metric illustrates the variance between the planned costs for the project and the actual cost for the project.  An example of the graph is shown below in figure 6.

Figure 6: Cost (Planned vs. Actual)

#### 4.2.1.2  Earned Value

The purpose of the Earned Value Metric is to compare the amount of work accomplished and the value of that work, to current and projected cost.  This is accomplished by comparing the planned cost; actual cost and the actual earned value of the deliverables accepted, then graphically representing the variance between the three.  Earned value is earned in increments of 25% when the phase or deliverable is started and the remaining 75% when the phase or deliverable is completed.  An example of the graph is shown below in figure 7.

Figure 7: Earned Value Management

#### 4.2.1.3  Margin

The purpose of this metric is to measure the projected margin percentage compared to the actual margin percentage that is being realized on the project.  Margin is the difference between the revenue for the project and the cost for the project.  At the beginning of each project senior management sets the desired baseline margin percentage expectation and the actuals are then tracked.  To illustrate this, the planned margin percentage is compared to the actual margin percentage.  An example of the graph is shown below in figure 8.

Figure 8: Margin

#### 4.2.1.4  Management Reserve Balance

The purpose of this metric is to measure the balance and expenditure of management reserve.  Management reserve is the portion of the contract budget that has been allocated to cover unforeseen program requirements.  During Project Close Out, any management reserve left increases the final margin for the project.  To illustrate this the graph shows the total amount of reserve left as well as the cumulative usage of the reserve on a monthly basis.  An example of the graph is shown below in figure 9.

Figure 9: Management Reserve Balance

### 4.2.2  Staffing Metrics

Staffing metrics are used throughout the life cycle of the project, included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Staffing | Start | PA | Staffing (Planned vs. Actual) | Monthly | Program Reviews & Formal Reviews |
|  | Start | PA | Staffing Mix (Salary, Hourly, Contractual) | Monthly | Program Reviews & Formal Reviews |
|  | Start | PA | Effort (Planned vs. Actual) | Monthly | Program Reviews & Formal Reviews |

#### 4.2.2.1  Staffing (Planned versus Actual)

The purpose of this metric is to measure how well the project is staffed according to plan.  This is accomplished by illustrating the variance between the planned staffing vs. the actual staffing for the project on a monthly basis.  An example of the graph is shown below in figure 10.

Figure 10: Staffing (Planned vs Actual)

#### 4.2.2.2  Staffing Mix (Salary, Hourly, Contractual)

The purpose of the metric is to illustrate the staffing mix on the project.  This is accomplished by showing the total number of people on the project categorized by salary, hourly and contractual employees.  The total number of employees on this graph must equal the total number of actual staffing in the Staffing (planned vs. actual) graph.  An example of the graph is shown below in figure 11.

Figure 11: Staffing Mix

#### 4.2.2.3  Effort (Planned VS. Actual)

The purpose of the metric is to measure the amount of effort being spent on the project.  This is accomplished by illustrating the amount of actual hours worked compared to the amount of planned hours and displaying their variance.  All time (including all overtime) must be logged for the projects.  An example of the graph is shown below in figure 12.

Figure 12: Effort (Planned vs. Actual)

### 4.2.3  Quality Metrics

Quality metrics are used throughout the life cycle of the project, included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Quality | Start | SQA | Deliverables (On Time vs. Late) | Weekly | Program Reviews & Formal Reviews |
|  | Start | SQA | Deliverables (Accepted vs. Rejected) | Weekly | Program Reviews & Formal Reviews |

#### 4.2.3.1  Deliverables (On Time vs. Late)

The purpose of the metric is to illustrate the project’s promptness of the delivery according to the approved schedule.  This is accomplished by showing the total number of deliverables that are on time compared to the ones that are late.  An example of the graph is shown below in figure 13.

Figure 13: Deliverables (On Time vs. Late)

#### 4.2.3.2  Deliverables (Accepted vs. Rejected)

The purpose of the metric is to measure the customer acceptance rate of the project deliverables.  This is accomplished by displaying the total number of deliverables that are accepted compared to the ones that are rejected.  An example of the graph is shown below in figure 14.

Figure 14: Deliverables (Accepted vs. Rejected)

### 4.2.4  Schedule Metrics

Schedule metrics are used throughout the life cycle of the project, included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Schedule | Start | PA | Deliverables (Total Number) | Monthly | Program Reviews & Formal Reviews |
|  | Start | PA | Deliverables (Complete/Remaining/Late) | Monthly | Program Reviews & Formal Reviews |
|  | Start | PA | Deliverables (Late/Aging) | Monthly | Program Reviews & Formal Reviews |

#### 4.2.4.1  Delivables (Total Number)

The purpose of the metric is to give a running total of deliveries for the project to the customer.  This is accomplished by showing the cumulative planned total number of deliveries (each time a deliverable flows to the customer for acceptance) vs. the actual number of deliveries that have acceptance letters.  An example of the graph is shown below in figure 15.

Figure 15: Deliverables (Planned vs. Actual)

#### 4.2.4.2  Deliverables (Complete/Remaining/Late)

The purpose of this metric is to measure the distribution of status the project deliverables. This is accomplished by categorizing the deliverables into completed, remaining or late.  An example of the graph is shown below in figure 16.

Figure 16: Deliverables (Complete/Remaining/Late)

#### 4.2.4.3  Deliverables (Late/Aging)

The purpose of this metric is to point out how many deliverables are late and the aging of those deliverables.  This is accomplished by categorizing the late deliverables into the following categories:  One, Two, Three or greater than Four weeks.  An example of the graph is shown below in figure 17.

Figure 17: Deliverables (Late/Aging)

### 4.2.5  Size Metrics

Size metrics are used throughout the life cycle of the project, included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Size | IRR | SCM | Function Points | By Phase | Formal Reviews |
| Size | IRR | SCM | Total Number of Requirements | By Phase | Formal Reviews |

#### 4.2.5.1  Function Points

The purpose of this metric is to track the project problem size throughout the life cycle.  This is accomplished by tracking the total number of function points on a monthly basis.  An example of the graph is shown below in figure 18.

Figure 18: Number of Function Points

#### 4.2.5.2  Total Number of Requirements

The purpose of this metric is to track the number of requirements throughout the life cycle of the project.  This is accomplished by tracking the requirements initially documented, along with any additional ones added throughout the life of the project.  An example of the graph is shown below in figure 19.

Figure 19: Number of Requirements

### 4.2.6  Change Request Metrics (CR)

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Change | IRR | SCM | Status (Approved, Rejected, Pending ) | Monthly | Program Reviews |
| Change | IRR | SCM | Cost Impact | Monthly | Program Reviews |
| Change | IRR | SCM | Categorization (Cost, Schedule, Quality) | Monthly | Program Reviews |

#### 4.2.6.1  Status (Approved, Rejected, Pending)

The purpose of the metric is to measure the status of all change requests.  This is accomplished by categorizing the change request into approved, rejected and pending.  An example of the graph is shown below in figure 20.

Figure 20: Change Requests (Approved/Rejected/Pending)

#### 4.2.6.2  Cost Impact

The purpose of the metric is to measure the total cost impact of all the changes.  This is accomplished by keeping a cumulative running total of all change requests and their associated cost.  An example of the graph is shown below in figure 21.

Figure 21: Cost Impact (Change Request)

.

### 4.2.7  Risks Metrics

Risk metrics are used throughout the life cycle of the software development process, included each month in the Project Status Report (PSR), and are briefed at the Program Reviews.

| Core Metric | When Start | Collector | Metric | Updated | Briefed At |
| --- | --- | --- | --- | --- | --- |
| Risk | Start | PA | Risk Open Distribution Aging Total Value | Monthly | Program Reviews |
| Risk | Start | PA | Action Items Open Distribution Aging | Monthly | Program Reviews |
| Risk | Start | PA | Issues Open Distribution Aging | Monthly | Program Reviews |

#### 4.2.7.1  Risks

##### 4.2.7.1.1  Open

The purpose of the metric is to measure how many risks are currently open on the project.  This is accomplished by showing the total number of open risk for each month.  An example of the graph is shown below in figure 22.

Figure 22: Number of Risks

##### 4.2.7.1.2  Distribution

The purpose of the metric is to illustrate the number of risks by category.  This is accomplished by assigning risks to one or more of the following areas:  Size, Schedule, Quality, Staffing, and/or Cost.  An example of the graph is shown below in figure 23.

Figure 23: Risks (Distribution)

##### 4.2.7.1.3  Aging

The purpose of the metric is to illustrate the age of the risk.  This is accomplished by categorizing the risk into the following aging groups:  One, Two, and > Three Months.  An example of the graph is shown below in figure 24.

Figure 24: Risk Aging

##### 4.2.7.1.4  Total Value

The purpose of the metric is to put a total value on the Risk.  This is accomplished by totaling the individual risk dollar amounts.  The total amount becomes known as the # of Dollars at Risk for the project.  An example of the graph is shown below in figure 25.

Figure 25: Number of Dollars at Risk

#### 4.2.7.2  Action Items

##### 4.2.7.2.1  Open

The purpose of the graph is to measure how many action items are open.  This is accomplished by showing the total number of open action items by time period.  An example of the graph is shown below in figure 26.

Figure 26: Number of Action Items

##### 4.2.7.2.2  Distribution

The purpose of the metric is to illustrate the number of action items by category.  This is accomplished by assigning action items to one or more of the following areas:  Size, Schedule, Quality, Staffing, and/or Cost.  An example of the graph is shown below in figure 27.

Figure 27: Action Items (Distribution)

##### 4.2.7.2.3  Aging

The purpose of the metric is to illustrate the aging of the action items.  This is accomplished by categorizing the action items into the following aging groups:  One, Two, and > Three Months.  An example of the graph is shown below in figure 28.

Figure 28: Action Item Aging

#### 4.2.7.3  Issues

##### 4.2.7.3.1  Open

The purpose of the graph is to measure how many Issues are open.  This is accomplished by showing the total number of open issues by time period.  An example of the graph is shown below in figure 29.

Figure 29: Number of Issues

##### 4.2.7.3.2  Distribution

The purpose of the metric is to illustrate the number of issues by category.  This is accomplished by assigning issues to one or more of the following areas:  Size, Schedule, Software Quality, Staffing, and/or Cost.  An example of the graph is shown below in figure 30.

Figure 30: Issues (Distribution)

##### 4.2.7.3.3  Aging

The purpose of the metric is to illustrate the aging of the issues.  This is accomplished by categorizing the issues into the following aging groups:  One, Two, and > Three Months.  An example of the graph is shown below.

Figure 31: Issue Aging

# 5.0  Status Accounting

Figure 32: Status Accounting

## 5.1  Reports

### 5.1.1  Weekly Status Meetings

Weekly status meetings and their formats are predefined under procedures for Project Tracking and Oversight.  The following metrics should be briefed using the Weekly Status Report (WSR) format with attachments for metric graphics.  Project Managers may opt to use all or a mixture of the metrics.  The following establishes a guideline for metrics to be reviewed during this review. Figure 32 illustrates this section in the context of the entire guidebook.

| Metric | Category | Product Code | Reported |
| --- | --- | --- | --- |
| Cost (Planned Versus Actual) | Cost | GP-MET-001 | Y |
| Earned Value | Cost | GP-MET-002 | Y |
| Margin | Cost | GP-MET-003 | N |
| Management Reserve Balance | Cost | GP-MET-004 | N |
| Staffing (Planned Versus Actual) | Staffing | GP-MET-005 | Y |
| Staffing Mix | Staffing | GP-MET-006 | Y |
| Effort | Staffing | GP-MET-007 | Y |
| Deliverables (On Time Versus Late) | Quality | GP-MET-008 | Y |
| Deliverables (Accepted Versus Rejected) | Quality | GP-MET-009 | Y |
| Deliverables (Total Number) | Schedule | GP-MET-010 | Y |
| Deliverables (Complete/Remaining/Late) | Schedule | GP-MET-011 | Y |
| Deliverables (Late/Aging) | Schedule | GP-MET-012 | Y |
| Function Point Size | Sizing | GP-MET-013 | N |
| Total Number of Requirements | Sizing | GP-MET-014 | N |
| CR Status (Approved, Rejected, Pending) | Change | GP-MET-015 | N |
| Cost Impact | Change | GP-MET-016 | N |
| CR Categorization (Cost, Schedule, Quality) | Change | GP-MET-017 | N |
| Risk Items Open | Risk | GP-MET-018 | Y |
| Risk Item Distribution | Risk | GP-MET-019 | Y |
| Risk Aging | Risk | GP-MET-020 | Y |
| Risk Total Value | Risk | GP-MET-021 | N |
| Issue Items Open | Risk | GP-MET-022 | Y |
| Issue Item Distribution | Risk | GP-MET-023 | Y |
| Issue Aging | Risk | GP-MET-024 | Y |
| Action Item Items Open | Risk | GP-MET-025 | Y |
| Action Item Item Distribution | Risk | GP-MET-026 | Y |
| Action Item Aging | Risk | GP-MET-027 | Y |

### 5.1.2  Program Reviews

Program Reviews are conducted monthly with the Program Manager in accordance with the Program Review procedure, Product Code: GP-PRC-200.  Program Managers may opt to use all or a mixture of the metrics.  The following establishes a guideline for metrics to be reviewed during this review.

| Metric | Category | Product Code | Reported |
| --- | --- | --- | --- |
| Cost (Planned Versus Actual) | Cost | GP-MET-001 | Y |
| Earned Value | Cost | GP-MET-002 | Y |
| Margin | Cost | GP-MET-003 | Y |
| Management Reserve Balance | Cost | GP-MET-004 | Y |
| Staffing (Planned Versus Actual) | Staffing | GP-MET-005 | Y |
| Staffing Mix | Staffing | GP-MET-006 | Y |
| Effort | Staffing | GP-MET-007 | Y |
| Deliverables (On Time Versus Late) | Quality | GP-MET-008 | Y |
| Deliverables (Accepted Versus Rejected) | Quality | GP-MET-009 | Y |
| Deliverables (Total Number) | Schedule | GP-MET-010 | Y |
| Deliverables (Complete/Remaining/Late) | Schedule | GP-MET-011 | Y |
| Deliverables (Late/Aging) | Schedule | GP-MET-012 | Y |
| Function Point Size | Sizing | GP-MET-013 | Y |
| Total Number of Requirements | Sizing | GP-MET-014 | Y |
| CR Status (Approved, Rejected, Pending) | Change | GP-MET-015 | Y |
| Cost Impact | Change | GP-MET-016 | Y |
| CR Categorization (Cost, Schedule, Quality) | Change | GP-MET-017 | Y |
| Risk Items Open | Risk | GP-MET-018 | Y |
| Risk Item Distribution | Risk | GP-MET-019 | Y |
| Risk Aging | Risk | GP-MET-020 | Y |
| Risk Total Value | Risk | GP-MET-021 | Y |
| Issue Items Open | Risk | GP-MET-022 | Y |
| Issue Item Distribution | Risk | GP-MET-023 | Y |
| Issue Aging | Risk | GP-MET-024 | Y |
| Action Item Items Open | Risk | GP-MET-025 | Y |
| Action Item Item Distribution | Risk | GP-MET-026 | Y |
| Action Item Aging | Risk | GP-MET-027 | Y |

### 5.1.3  Formal Reviews

Formal Reviews are conducted at the end of each phase of the project.  Program Managers may opt to use all or a mixture of the metrics.  The following establishes a guideline for metrics to be reviewed during this review.

| Metric | Category | Product Code | Reported |
| --- | --- | --- | --- |
| Cost (Planned Versus Actual) | Cost | GP-MET-001 | Y |
| Earned Value | Cost | GP-MET-002 | Y |
| Margin | Cost | GP-MET-003 | N |
| Management Reserve Balance | Cost | GP-MET-004 | N |
| Staffing (Planned Versus Actual) | Staffing | GP-MET-005 | Y |
| Staffing Mix | Staffing | GP-MET-006 | Y |
| Effort | Staffing | GP-MET-007 | Y |
| Deliverables (On Time Versus Late) | Quality | GP-MET-008 | Y |
| Deliverables (Accepted Versus Rejected) | Quality | GP-MET-009 | Y |
| Deliverables (Total Number) | Schedule | GP-MET-010 | Y |
| Deliverables (Complete/Remaining/Late) | Schedule | GP-MET-011 | Y |
| Deliverables (Late/Aging) | Schedule | GP-MET-012 | Y |
| Function Point Size | Sizing | GP-MET-013 | Y |
| Total Number of Requirements | Sizing | GP-MET-014 | Y |
| CR Status (Approved, Rejected, Pending) | Change | GP-MET-015 | Y |
| Cost Impact | Change | GP-MET-016 | Y |
| CR Categorization (Cost, Schedule, Quality) | Change | GP-MET-017 | Y |
| Risk Items Open | Risk | GP-MET-018 | Y |
| Risk Item Distribution | Risk | GP-MET-019 | Y |
| Risk Aging | Risk | GP-MET-020 | Y |
| Risk Total Value | Risk | GP-MET-021 | Y |
| Issue Items Open | Risk | GP-MET-022 | Y |
| Issue Item Distribution | Risk | GP-MET-023 | Y |
| Issue Aging | Risk | GP-MET-024 | Y |
| Action Item Items Open | Risk | GP-MET-025 | Y |
| Action Item Item Distribution | Risk | GP-MET-026 | Y |
| Action Item Aging | Risk | GP-MET-027 | Y |

## 5.2  Checklists

QA Checklist for Metrics, Product Code:  GTA-PMO-CKL-035 will be used to crosscheck metrics prior to presentation for any review.

# 6.0  Supporting Reviews and Audits

Figure 33: Supporting Reviews and Audits

## 6.1  Reviews

For information concerning reviews of metrics, reference section 5.0 for detailed information. Figure 33 illustrates this section in the context of the entire guidebook.

## 6.2  Audits

Audits will be conducted on metrics as determined by the GTA PMO for the Georgia Technology Authority.

# Footnotes

This document is written and produced by the Georgia Technology Authority (GTA), Program  Management Office (PMO) as part of the strategic Continuous Process Improvement initiative.  Questions or recommendations for improvement to this document may be forwarded to any PMO member.