## Instructions
Instructions:
This spreadsheet calculates Schedule Performance Index (SPI) based on deliverables and milestones.
Use the "Report" worksheet to help calculate Schedule Performance Index (SPI): *(DO NOT EDIT FORMULA CELLS)
Directions
1. Enter the values in the "orange" cells in the following order:
a. | AS OF DATE | (mm/dd/yyyy)
b.Deliverable/Milestone Name | Deliverable/Milestone Name
c. | Start Date | (mm/dd/yyyy)
d. | Finish Date | (mm/dd/yyyy)
e. | Cost (hrs or $'s) Actual contract cost of the work deliverable.
f. | Percent Complete Percent complete for the deliverable as of the "As Of Date".
g. | AC (hrs or $'s) Actual Cost of Work Performed. Reflects the actual cost incurred to produce the Earned Value (EV) of the deliverable. *NOTE: For Fixed Fee projects where the vendor is not reporting actual effort spent in developing the deliverable, the Actual Cost of Work performed is derived from the number of days between the Start Date of the Deliverable and the As Of Date. Because the cost of the deliverable is fixed for fixed-fee projects, the Actual Cost of Work Performed will not exceed the cost of the deliverable.
2. Insert additional rows before the "Totals" row and copy the formulas from previous cell
3. Delete additional rows
View "Summary" worksheet for a summary of Project progress
View "Sample Report" worksheet for an example of a completed report
View "Sample Summary" worksheet for an example of a completed summary of the sample report/project progress
View "Definitions" worksheet for a definition of terms and formulas

## Report
AS OF DATE:
|  | (a) | (b) | (c) | (d) | (e) | (f) (e * (d / c)) | (g) | (h) (e - g) | (i) | (j) (h - i) |  | (k) (h - f) |  | (l) | (m) (h / i) | (n) (h / f) | (o) (m * n)
# | Deliverable/Milestone | Start Date: (From MS Project) | Finish Date: (From MS Project) | Duration (Work Days) | Duration Days Used | Cost (hrs or $'s) | PV (hrs or $'s) | Percent Complete | EV (hrs or $'s) | AC (hrs or $'s) | Cost Variance | Cost Variance % | Schedule Variance | Schedule Variance % | EAC | CPI | SPI | CR | ← Click "triangle" to view the comments/description
Project Title
1 | Deliverable/Milestone 1 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
2 | Deliverable/Milestone 2 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
4 | Deliverable/Milestone 3 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
3 | Deliverable/Milestone 4 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
5 | Deliverable/Milestone 5 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
6 | Deliverable/Milestone 6 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
7 | Deliverable/Milestone 7 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
8 | Deliverable/Milestone 8 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
9 | Deliverable/Milestone 9 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
10 | Deliverable/Milestone 10 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
11 | Deliverable/Milestone 11 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
12 | Deliverable/Milestone 12 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
13 | Deliverable/Milestone 13 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
14 | Deliverable/Milestone 14 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
15 | Deliverable/Milestone 15 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
16 | Deliverable/Milestone 16 |  |  |  | 0 |  | #VALUE! |  | 0 |  | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | ← To add more Deliverables/Milestones, insert rows above this one. You can or delete this row after you are done adding Deliverables/Milestones.
TOTALS |  | 0 | 0 |  | 0 | 0 | #VALUE! | #VALUE! | 0 | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! |  | #VALUE!
Formulas:
Duration (Work Days) = IF(AND([Start Date: (From MS Project)]>0,[Finish Date: (From MS Project)]>0),NETWORKDAYS([Start Date: (From MS Project)],[Finish Date: (From MS Project)],P1),"")
Duration (Work Days) = IF(AND([Start Date: (From MS Project)]>0,[Finish Date: (From MS Project)]>0),NETWORKDAYS([Start Date: (From MS Project)],[Finish Date: (From MS Project)]),"")
Duration Days Used = IF([Start Date: (From MS Project)]>P1,0,IF([Finish Date: (From MS Project)]<P1,[Duration (Work Days)],NETWORKDAYS([Start Date: (From MS Project)],P1)))
Start Date: (From MS Project) = MIN(C5:[Start Date: (From MS Project), row above])
Finish Date: (From MS Project) = MAX(D5:[Finish Date: (From MS Project), row above])
Note on E3: Net working days including holidays between the Start Date and the Finish Date of the work task or deliverable.
Note on F3: Number of working days between the Start Date and the "As Of Date" used for reporting purposes.
Note on G3: Actual contract cost of the work task or deliverable.
Note on H3: Budgeted Cost of Work Scheduled (PV). The total budgeted cost of the deliverable through the "As Of Date". Used to determine how much work should have been completed by the "As Of Date". If the "As Of Date" is greater than the planned Finish Date of the deliverable, the PV is equal to the deliverable cost. If the "As Of Date" is less than the Start Date, the PV should be equal to zero.
Note on I3: Percent complete for the deliverable as of the "As Of Date".
Note on J3: Budgeted Cost of Work Performed (EV). Also referred to as the Earned Value. Used to determine how much of the cost originally budgeted for the deliverable has been accomplished by the "As Of Date". EV is calculated by multiplying the Deliverable Cost times the percent complete. When the deliverable is 100% complete, the EV will be equal to the Budget Cost.
Note on K3: Actual Cost of Work Performed. Reflects the actual cost incurred to produce the Earned Value (EV) of the deliverable. NOTE: For Fixed Fee projects where the vendor is not reporting actuals effort spent in developing the deliverable, the Actual Cost of Work performed is derived from the number of days between the Start Date of the Deliverable and the As Of Date. Because the cost of the deliverable is fixed for fixed-fee projects, the Actual Cost of Work Performed will not exceed the cost of the deliverable.
Note on L3: Cost Variance. Determined by the formula: CV = EV – AC) A negative Cost Variance is considered a "bad" variance.
Note on N3: Schedule Variance. Determined by the formula: SV = EV – PV A negative Schedule Variance is considered a "bad" variance.
Note on Q3: Cost Performance Index. A measure of cost efficiency of the project. Determined by the formula: CPI = EV / AC If EV and actual cost are equal, the CPI will be 100% (i.e. all work completed on budget).
Note on R3: Schedule Performance Index. A measure of schedule efficiency of the project. Determined by the formula: SPI = EV / PV If EV and PV are equal, the SPI will be 100% (i.e. all work scheduled is performed as scheduled). Status of SPI GREEN = On track >=1.0 YELLOW = Slightly behind schedule or budget >0.85 RED = Needs immediate attention >0.65 BLACK = Candidate for Leadership Action <0.65
Note on S3: Critical Ratio. A measure of the efficiency of the project when both the schedule performance and cost performance indices are taken into account. Determined by the formula: CR = CPI * SPI

## Summary
Line #
1. | Project Name | PROJECT NAME
2. | Project start date (MM/DD/YYYY): | 0
3. | Project end date (MM/DD/YYYY): | 0
4. | Total project duration (working days) |  | Days
5. | Reporting As Of Date | 0
6. | Project days consumed through "As Of Date" | 0 | Days | Percent | #VALUE!
7. | Budgeted Project Cost | 0 | Dollars
8. | Project Estimate At Completion (EAC) | 0 | Dollars
9. | Earned Value through As Of Date | #VALUE! | Dollars
10. | Planned Value through As Of Date | 0 | Dollars | Percent | #DIV/0!
11. | Actual Cost through As Of Date | NA
12. | Cost Variance | N/A |  | CPI | N/A
13. | Schedule Variance | #VALUE! | Dollars | SPI | #VALUE!
14. | Forecast Duration Under (Over) Plan | #VALUE! | Days
Work packages with significant variance (less than -10% or SPI < 90%)
Variance
| Deliverables Or Milestones | Start | Finish | % | SPI
1
2
3
4
5

## "Sample" Report
[13 empty] | AS OF DATE: |  | 2008-04-01
|  | (a) | (b) | (c) | (d) | (e) | (f) (e * (d / c)) | (g) | (h) (e - g) | (i) | (j) (h - i) |  | (k) (h - f) |  | (l) | (m) (h / i) | (n) (h / f) | (o) (m * n)
# | Deliverable/Milestone | Start Date: (From MS Project) | Finish Date: (From MS Project) | Duration (Work Days) | Duration Days Used | Cost (hrs or $'s) | PV (hrs or $'s) | Percent Complete | EV (hrs or $'s) | AC (hrs or $'s) | Cost Variance | Cost Variance % | Schedule Variance | Schedule Variance % | EAC | CPI | SPI | CR
Project Title
1 | Deliverable/Milestone 1 | 2007-09-10 | 2007-10-11 | 24 | 24 | 33920 | 33920 | 100% | 33920 | 32000 | 1920 | 94.34% | 0 | 0% | 32000 | 106% | 1
2 | Deliverable/Milestone 2 | 2007-09-10 | 2007-11-30 | 60 | 60 | 191730 | 191730 | 100% | 191730 | 191000 | 730 | 99.62% | 0 | 0% | 191000 | 100.4% | 1
4 | Deliverable/Milestone 3 | 2007-11-05 | 2008-04-02 | 107 | 107 | 106516.67 | 106517 | 98% | 104386 | 106517 | -2131 | 100% | -2131 | -2.001% | 108691.1668 | 98% | 0.97999
3 | Deliverable/Milestone 4 | 2007-09-10 | 2007-11-30 | 60 | 60 | 127820 | 127820 | 100% | 127820 | 127820 | 0 | 100% | 0 | 0% | 127820 | 100% | 1
5 | Deliverable/Milestone 5 | 2008-03-17 | 2008-04-17 | 23 | 12 | 144984.1667 | 75644 | 31% | 44945 | 144984 | -100039 | 100% | -30699 | -21.17% | 467691.2764 | 31% | 0.59416
6 | Deliverable/Milestone 6 | 2007-11-05 | 2008-04-02 | 107 | 107 | 63510.8333 | 63511 | 98% | 62241 | 63511 | -1270 | 100% | -1270 | -2% | 64806.7437 | 98% | 0.98
7 | Deliverable/Milestone 7 | 2008-03-17 | 2008-04-17 | 23 | 12 | 104155.8333 | 54342 | 31% | 32288 | 105000 | -72712 | 100.8% | -22054 | -21.17% | 338712.9119 | 30.75% | 0.59416
8 | Deliverable/Milestone 8 | 2007-09-10 | 2007-10-08 | 21 | 21 | 10000 | 10000 | 100% | 10000 | 15000 | -5000 | 150% | 0 | 0% | 15000 | 66.67% | 1
9 | Deliverable/Milestone 9 | 2007-09-10 | 2007-10-30 | 37 | 37 | 25000 | 25000 | 100% | 25000 | 23000 | 2000 | 92% | 0 | 0% | 23000 | 108.7% | 1
10 | Deliverable/Milestone 10 | 2007-09-10 | 2007-11-06 | 42 | 42 | 10000 | 10000 | 100% | 10000 | 10000 | 0 | 100% | 0 | 0% | 10000 | 100% | 1
11 | Deliverable/Milestone 11 | 2007-09-10 | 2007-11-29 | 59 | 59 | 15000 | 15000 | 89% | 13350 | 16000 | -2650 | 106.7% | -1650 | -11% | 17977.5281 | 83.44% | 0.89
12 | Deliverable/Milestone 12 | 2007-10-31 | 2007-11-28 | 21 | 21 | 15000 | 15000 | 100% | 15000 | 15500 | -500 | 103.3% | 0 | 0% | 15500 | 96.77% | 1
13 | Deliverable/Milestone 13 | 2007-11-30 | 2008-03-03 | 67 | 67 | 50000 | 50000 | 100% | 50000 | 45000 | 5000 | 90% | 0 | 0% | 45000 | 111.1% | 1
14 | Deliverable/Milestone 14 | 2008-01-22 | 2008-03-18 | 41 | 41 | 25000 | 25000 | 96% | 24000 | 22000 | 2000 | 88% | -1000 | -4% | 22916.6667 | 109.1% | 0.96
15 | Deliverable/Milestone 15 | 2007-11-30 | 2008-03-03 | 67 | 67 | 25000 | 25000 | 100% | 25000 | 25000 | 0 | 100% | 0 | 0% | 25000 | 100% | 1
16 | Deliverable/Milestone 16 | 2007-12-30 | 2008-03-15 | 55 | 55 | 25000 | 25000 | 80% | 20000 | 25000 | -5000 | 100% | -5000 | -20% | 31250 | 80% | 0.8 |  | ← To add more Deliverables/Milestones, insert rows above this one. You can or delete this row after you are done adding Deliverables/Milestones.
TOTAL |  | 2007-09-10 | 2008-04-17 | 158 | 147 | 972637.5033 | 853484 | 92.52% | 789680 | 967332 | -177652 | 99.45% | -63804 | -6.56% | 1191448.9178 | 81.63% | 0.92524
Formulas:
Duration (Work Days) = IF(AND([Start Date: (From MS Project)]>0,[Finish Date: (From MS Project)]>0),NETWORKDAYS([Start Date: (From MS Project)],[Finish Date: (From MS Project)],P1),"")
Duration (Work Days) = IF(AND([Start Date: (From MS Project)]>0,[Finish Date: (From MS Project)]>0),NETWORKDAYS([Start Date: (From MS Project)],[Finish Date: (From MS Project)]),"")
Duration Days Used = IF([Start Date: (From MS Project)]>P1,0,IF([Finish Date: (From MS Project)]<P1,[Duration (Work Days)],NETWORKDAYS([Start Date: (From MS Project)],P1)))
Start Date: (From MS Project) = MIN(C5:[Start Date: (From MS Project), row above])
Finish Date: (From MS Project) = MAX(D5:[Finish Date: (From MS Project), row above])
Note on E3: Net working days including holidays between the Start Date and the Finish Date of the work task or deliverable.
Note on F3: Number of working days between the Start Date and the "As Of Date" used for reporting purposes.
Note on G3: Actual contract cost of the work task or deliverable.
Note on H3: Budgeted Cost of Work Scheduled (PV). The total budgeted cost of the deliverable through the "As Of Date". Used to determine how much work should have been completed by the "As Of Date". If the "As Of Date" is greater than the planned Finish Date of the deliverable, the PV is equal to the deliverable cost. If the "As Of Date" is less than the Start Date, the PV should be equal to zero.
Note on I3: Percent complete for the deliverable as of the "As Of Date".
Note on J3: Budgeted Cost of Work Performed (EV). Also referred to as the Earned Value. Used to determine how much of the cost originally budgeted for the deliverable has been accomplished by the "As Of Date". EV is calculated by multiplying the Deliverable Cost times the percent complete. When the deliverable is 100% complete, the EV will be equal to the Budget Cost.
Note on K3: Actual Cost of Work Performed. Reflects the actual cost incurred to produce the Earned Value (EV) of the deliverable. NOTE: For Fixed Fee projects where the vendor is not reporting actuals effort spent in developing the deliverable, the Actual Cost of Work performed is derived from the number of days between the Start Date of the Deliverable and the As Of Date. Because the cost of the deliverable is fixed for fixed-fee projects, the Actual Cost of Work Performed will not exceed the cost of the deliverable.
Note on L3: Cost Variance. Determined by the formula: CV = EV – AC) A negative Cost Variance is considered a "bad" variance.
Note on N3: Schedule Variance. Determined by the formula: SV = EV – PV A negative Schedule Variance is considered a "bad" variance.
Note on Q3: Cost Performance Index. A measure of cost efficiency of the project. Determined by the formula: CPI = EV / AC If EV and actual cost are equal, the CPI will be 100% (i.e. all work completed on budget).
Note on R3: Schedule Performance Index. A measure of schedule efficiency of the project. Determined by the formula: SPI = EV / PV If EV and PV are equal, the SPI will be 100% (i.e. all work scheduled is performed as scheduled). Status of SPI GREEN = On track >=1.0 YELLOW = Slightly behind schedule or budget >0.85 RED = Needs immediate attention >0.65 BLACK = Candidate for Leadership Action <0.65
Note on S3: Critical Ratio. A measure of the efficiency of the project when both the schedule performance and cost performance indices are taken into account. Determined by the formula: CR = CPI * SPI

## "Sample" Summary
Line #
1. | Project Name | PROJECT NAME
2. | Project start date (MM/DD/YYYY): | 2007-09-10
3. | Project end date (MM/DD/YYYY): | 2008-04-17
4. | Total project duration (working days) | 158 | Days
5. | Reporting As Of Date | 2008-04-01
6. | Project days consumed through "As Of Date" | 147 | Days | Percent | 93.04%
7. | Budgeted Project Cost | 972637.5033 | Dollars
8. | Project Estimate At Completion (EAC) | 972637.5033 | Dollars
9. | Earned Value through As Of Date | 853484 | Dollars
10. | Planned Value through As Of Date | 789680 | Dollars | Percent | 81.19%
11. | Actual Cost through As Of Date | NA
12. | Cost Variance | N/A |  | CPI | N/A
13. | Schedule Variance | -63804 | Dollars | SPI | 0.92524
14. | Forecast Duration Under (Over) Plan | -12.766 | Days
Work packages with significant variance (less than -10% or SPI < 90%)
Variance
| Deliverables Or Milestones | Start | Finish | % | SPI
1 | Deliverable/Milestone 5 | 2008-03-17 | 2008-04-17 | -21.17% | 59.42%
2 | Deliverable/Milestone 7 | 2008-03-17 | 2008-04-17 | -21.17% | 59.42%
3
4
5

## Definitions
Project Earned Value Analysis
Project Earned Value Analysis measures the health of a project by looking at cost information and schedule information concurrently. It tells you whether the project is on schedule and on budget, as well as whether the project is on budget for the amount of work done so far.
Metric | Abbrev. | Description | Formula/Value
Budget at Completion | BAC | Baseline cost for 100% of project. | N/A
Actual Cost | AC | Total costs actually incurred. | N/A
Earned Value | EV | Amount of budget earned so far based on physical work accomplished, without reference to actual costs. | Earned Value = % of completed work X BAC
Planned Value | PV | The budget for the physical work scheduled to be completed by the end of the time period. | Planned Value = (Planned % Complete) X (BAC)
Cost Variance | CV | Measure of cost overrun. The difference between the budget for the work actually done so far and the actual costs. | Earned Value–Actual Cost EV–AC
Cost Performance Index | CPI | Cost efficiency ratio. A CPI of 1.00 means that the costs so far are exactly the same as the budget for work actually done. | Earned Value/ Actual Cost EV/AC
Schedule Variance | SV | Measure of schedule slippage. The difference between the budget for the work actually done so far and the budgeted cost of work scheduled. | Earned Value–Planned Value EV–PV
Schedule Performance Index | SPI | The schedule efficiency ratio. An SPI of 1.0 means that the project is exactly on schedule. | Earned Value/Planned Value EV/PV
Estimate to Completion | ETC | The expected additional cost to complete. | Estimate at Completion–Actual Cost EAC–AC
Estimate at Completion | EAC | Expected total cost based on the current cost efficiency ratio. | Budget at Completion/Cost Performance Index BAC/CPI
Variance at Completion | VAC | Estimated cost overrun at the end of project. | Budget at Completion–Estimate at Completion BAC–EAC
Status of SPI
|  | GREEN = On track | 0.9 - 1.0
|  | YELLOW = Slightly behind schedule or budget | .80 - .89
|  | RED = Needs immediate attention | < 0.80
Holidays:
New Year’s Day
Martin Luther King, Jr.’s Birthday
Confederate Day
Memorial Day
Independence Day
Labor Day
Columbus Day
Veterans Day
Thanksgiving Day
Robert E. Lee's Birthday
Christmas Day
Washington's Birthday