## Slide 1: Georgia Enterprise Management Suite (GEMS) Training
Created & Presented by GTA EPMO
Hank Oelze, PMP 404-463-5303
Version 3.5

## Slide 2: GEMS Origin
“Agencies told us they needed help keeping large projects on track,” said Tom Fruman, director of GTA's Enterprise Governance and Planning Division. “We believe this portfolio and project management system will give them insight they didn't have before. They will be able to monitor the health and status of projects using a combination of traditional operational data and qualitative assessment data from multiple stakeholders.”
GEMS includes selected modules from CAI's project portfolio management application, ITBuzz Enterprise Management Suite, which provides visibility and analytics for the purpose of risk alerts and avoidance. CAI refers to the tool/application as: Advanced Management Insight (AMI).
GTA has opted to use the Portfolio Management, Automated Project Office, and Issues Resolution Management modules.

## Slide 3: What’s New in GEM Training Version 3.5?
Removed redundant slides (adding people, roles, etc.)
Eliminated unessential slides, e.g., tool to EPLC alignment, downloading attachments
Added slides based on user input, e.g., delete an issue
Updated Issue & Risk sections
Added Project Portfolio Questionnaire option

## Slide 4
Process Flow
PPM
APO

## Slide 5: Training Index
PPM Slides 6-64
Adding Resources 22
Scheduling a Questionnaire 32
APO Slides 65-109
Issues 68
Risks 81
Stage Gate Reviews 94
Critical Panel 107

## Slide 6: GEMS Phase I Training
PPM – Proposal, New Projects Phase

## Slide 7: PPM Versus APO
Easiest Way to Remember GEMS Process:
PPM (Project Portfolio Management) is Proposal Phase
APO (Automated Project Office) is Project Phase

## Slide 8: Initial Login Screen - Video

## Slide 9: Creating a Proposal or Project - Video

## Slide 10: Initial Screen – GEMS

## Slide 11: Create a New Proposal or Project
Select “add project”
+

## Slide 12: Select Project Type then Next
Select App Dev
IMPORTANT

## Slide 13: Project Types
1. Select “Projects” Tab
2. Select “Project Types”

## Slide 14: Project Types
Drop Down Choices

## Slide 15: New Project Entry Screen Appears

## Slide 16: Enter Profile Basic Fields
ID: Three letter agency ID – YYYYMMDD (DOR-20140828)*
Name: Descriptive Name
Owning Organization: Select from Drop Down
Questionnaire Scheduling: Select “Enabled” from Drop Down
Sponsoring Organization: Select from Drop Down
Project Phase: Initiate, if this is a new project
Description: Short description of project
Budget: 1287345 ALL cost amounts are entered without $, no commas, whole dollars only.
* If multiple entries occur in one day add suffix(a,b,c etc.)
Fields with an asterisk (*) are mandatory.
Notes: Describe the difference between Owning and Sponsoring organizations (they can be the same)
The Sponsoring Organization is not a required field, but should be completed. The name is used in some e-mail notifications throughout the system.

## Slide 17: Warning Message, Select OK

## Slide 18: Profile Data Screens
This initiation information was previously captured in the APR. If you are using GEMS, you will no longer be required to submit a separate APR.
Basic Fields
Initiation
Project Data
Notes: The old APR form has been replaced by completing these fields
If you are using GEMS, you will no longer be required to submit a separate APR

## Slide 19: Enter Initiation Data
Business Owner: Someone in your Agency
Submission Date: Today’s Date (6/21/2014 format)
Describe the Business Problems to be Solved: Enter text
What are the Business Drivers: Enter Text
Identify agency strategy supported: Enter Text
Identify any existing application/system Impacted: Enter Text
Where are you in the process? Select from dropdown
What is the expected source of funds for this? Select from dropdown
Are the funds currently committed or requested? Select from dropdown
Anticipated time to begin implementation: Enter year YYYY
Is there a hard time constraint (deadline)? Select YES/No
If yes, what is the date: Enter 6/30/2015 format
What benefits will this investment provide? Enter Text
Planning Budget: Enter whole number Implementation Budget: whole number
Discretionary Option: Select from dropdown Alignment: Select from dropdown
Notes: The Business Owner should be the business executive in your organization that is accountable for the success of the program this technology will support
You might want to highlight the fields that will populate the PPM dashboard so they can see the relationship later
Agency Strategy should be the strategy in your agency strategic plan that this proposal is aligned with (alignment with the state strategies is identified in a later field – “Alignment”)
Planning budget will be used primarily for federally funded projects where funding is provided through a PAPD or long-term
Define “Discretionary Option”

## Slide 20: Scroll Down to Project Data

## Slide 21: Enter Project Data
Many of these fields may be unknown during this planning phase of the project, if so, leave them blank.
Flow Status: Select “Proposed”* from the Drop Down
Planned Baseline Start: mm/dd/yyyy format
Planned/Baseline Completion Date: mm/dd/yyyy format
Original Project Budget:
Estimated Funds Needed to Complete Project: Enter whole dollars
Click “SAVE” on bottom right corner.
* Status must be changed to Proposed to view on Dashboard

## Slide 22: Assign Resources & Roles - Video

## Slide 23: Search for Project (Proposal)
1. Select “Projects”
2. Enter search criteria (Name or Agency)
3. Click Search
4. Results

## Slide 24: Select Project
Double click on the Project Name

## Slide 25: Select Assignments, Option A
Select Assignments Icon

## Slide 26: Select Assignments, Option B
Select Project & “Assignments”

## Slide 27: Select Assign People
Note: if the person you want to assign is not listed send their: first name, last name, organization and email address to the support team listed at the end of this presentation.

## Slide 28: Select People & Roles
Select People and Role from Drop Down
At a minimum, you MUST assign a Sponsor, PM/PMO, CIO and a Business Owner
Select Assign Selected People
Note: List contains all system resources

## Slide 29: Assign All Roles and Save
All resources MUST be assigned a role in order to save.

## Slide 30: Validate Assignments
Verify People & Roles

## Slide 31: Proposal Evaluation
Once the resources are assigned, they can be sent questionnaires in order to evaluate the validity of the proposal.
The questionnaires may (and should) be sent out repeatedly as the evaluation process occurs.
The PPM questionnaires are focused on the alignment of the Business Case to the proposed solution.

## Slide 32: Manually Scheduling a Questionnaire - Video

## Slide 33: Schedule PPM Validation Questionnaire
2. Enter your search criteria
4. Double click on your project
1. Select Projects, Find/Create Projects
3. Select Search

## Slide 34: Schedule Questionnaire
Click on the Questionnaires Link

## Slide 35: Schedule Questionnaire
Click on Schedule Questionnaire Manually button
NOTE: Initially, agencies can only schedule questionnaires manually. Event-triggered questionnaires (CPR) will be managed by GTA

## Slide 36: Complete Questionnaire Screen
1. Select Project Data
2. Default is Standard
3. Select PPM Validation Review from Drop Down
4. Insert today’s date
8. Select Next
NOTE: The system will default to having the questionnaires pre-populated with answers from earlier iterations. If you do not want this option, remove the checkmark.
7. Enter the reason for Questionnaire
6. Enter “1”
5. Enter “5”

## Slide 37: Select Respondents
1. Select agency from Drop Down
2. Select Individuals to receive questionnaires
Select OK
NOTE: Only individuals assigned to the project display

## Slide 38: Questionnaire Validation
1. Verify: Two questionnaires scheduled

## Slide 39: Responding to a Questionnaire - Video

## Slide 40: Questionnaire email
5. Click on this link
1. You will receive an automated email from GEMS
2. Verify Project
3. Verify questionnaire
4. This displays “Reason for Scheduling” text

## Slide 41: Questionnaire Response
Click on Begin Assessment

## Slide 42: Begin Assessment
Answer All questions
NOTE: For those questions followed by a text box, text is required. The system will not allow you to move forward without entering text.

## Slide 43: Assessment Complete
Progress Indicators
1. Submit
2. Save & Exit
3. Discard & Exit
Three Options:

## Slide 44: Assessment Complete
NOTE: You will need to wait until the Production site is updated (48 minutes after the hour) to view results of questionnaire response.

## Slide 45: Validate Proposal Responses
1. Select Dashboards, and then PPM
2. Select the Project Proposal Tab
3. Select Project and then your project from drop down

## Slide 46: View Proposal

## Slide 47: Review PPM Dashboard - Video

## Slide 48: PPM Dashboard
1. Select Dashboards, PPM
2. Click on Proposal Validation Tab
2. Select Proposal Validation

## Slide 49: Validate Results
1. Select Project
2. Check Overall Score
3. Verify Attachment. (Business Case)
4. Confirm Due Diligence Score
5. Exit Dashboard

## Slide 50: Validate Results - Video

## Slide 51: Send Out Additional PPM Questionnaires
The following PPM-Specific Questionnaires should be manually sent to each of your team members. You can send a single questionnaire to multiple people. For example, the Business Owner and Business Analysts can be sent the PPM-Business-Business Owner questionnaire.
    PPM-Business-Business Owner
    PPM-Business-Sponsor
    PPM-CIO
    PPM-IT-Development
    PPM-IT-Support
    PPM-PMO

## Slide 52: Send Out Additional Questionnaires
At this stage you may want to add additional project resources, architect roles for example, that may not have been assigned during the early initiation phase.
The process is the same, add the resource from the GEMS pool to your project and send them a manual questionnaire.

## Slide 53: Verify Questionnaire Results - Video

## Slide 54: Proposal Scores
Review Scores based on Questionnaires

## Slide 55: Evaluate Specific Questions - Video

## Slide 56: Move from Proposal (PPM) to Project (APO)
Verify the completeness of the data.
Update Project Data as Necessary
Add additional resources and/or roles
Assign a “System PM” if your project is selected for the monthly Enterprise Critical Panel Review (name displays on CPR Dashboard)
Confirm project flow status was moved from “Proposed” to “Active”

## Slide 57: Adding a Critical Panel PM
You can assign a System Project Manager, Critical Panel PM & PMO; however the PMO will not receive the monthly PM status and comments questionnaires.
3 Separate “PM” Roles

## Slide 58: Complete Gate 1 (Major Milestone)
Option 1:
Send a Manual Questionnaire for Gate 1 to PM
NOTE: 2 Options for Gate 1

## Slide 59: Complete Gate 1 (Major Milestone)
Option 2
Change Project Phase to Design
Gate 1 Questionnaire will automatically be sent to PM/PMO.

## Slide 60: Confirm Gate 1
1. Select Dashboards PPM
3. Select Project from Drop Down
4. Confirm Gate Progression
2. Select Gate 1 Tab

## Slide 61: Approve and Unapprove Projects - Video

## Slide 62: Approve Project
3. Select Approve Project
1. Select Proposal Validation Tab in PPM
2. Select your Project

## Slide 63: Approval Validation
Check Mark (In-flight) = Approved Project
1. Select Master Selection Tab
2. Select your Project
Note: You must wait for the refresh for the  to appear

## Slide 64: PPM Summary
Congratulations!
You have entered a proposal, assigned resources to evaluate the proposed project, received evaluations from key stakeholders, completed Gate 1 and approved the project.
The implementation phase and all subsequent phases are monitored through the APO (Automated Project Office) view.

## Slide 65: GEMS Phase II Training
APO – New Projects Phase

## Slide 66: PM Responsibilities
Monitor gate reviews
Create/change project assignments (at a minimum add a Team Lead and/or Team Member)
Review questionnaire responses
Evaluate project on APO Dashboard
Log and manage issues
Log and manage risks
Perform monthly project updates
  Schedule
  Budget
  Critical Project Comments (as required)

## Slide 67: Monitor Project - Video

## Slide 68: Issue Management

## Slide 69: Manage Issues
2. Select Issues
1. Select your project

## Slide 70: Create An Issue - Video

## Slide 71: Create a New Issue
Select add issue

## Slide 72: Enter New Issue
1. Enter Title
2. Enter
Classification
3. Confirm Requestor
4. Enter
Description
5. Describe Impact
6. Select
Priority
7. Enter due date
8. Select
Severity
9. Enter Resolution Date
10. Select person to resolve issue

## Slide 73: Finalize Issue
1. Add additional contributors as necessary
2. Add attachments as necessary
3. Click Save

## Slide 74: Completed Issue

## Slide 75: Issue Assignment email

## Slide 76: Responding to Issue email notification
If you receive a notification you must either accept or reject the assignment by clicking the link on the email.
Anyone can be assigned an issue, you DO NOT need access to GEMS to accept, comment or close an issue.
Once you log in to GEMS a dialog box will display and you may enter text describing the issue resolution.

## Slide 77: Issue - Update and Accept - Video

## Slide 78: Notification of Unassigned Issue
Your action would be to reassign the Issue

## Slide 79: Issue Report, Track and Close - Video

## Slide 80: Issue Management
If you need to close an issue and the assignee is no longer available, assign the issue to yourself (as PM). You then have the ability to reassign or close the issue.
Issues should be reviewed once a month, at a minimum.

## Slide 81: Risk Management

## Slide 82: Risk Management - Option 1 Keyed
Select the Risk Tab
Select add risk

## Slide 83: Risk Management - Option 1 Keyed
Select the Risk Tab
Select add risk
Complete all fields
Select Save when complete
Repeat process for all key risks
Update monthly

## Slide 84: Risk Management - Option 2 Import
Best method for 10+ risks
You must use the standard template (Excel) it contains dropdowns to facilitate the import
Mandatory Fields (cannot exceed 255 characters in length):
Project ID Mitigation Strategy
Risk Id Risk Owner
Risk Title Last Risk Review
Risk Description Risk Number
Probability Risk Status
Impact
Save your Excel file as a CSV (Comma delimited)
Risks can be imported as often as necessary or you can update via Risk tab

## Slide 85: Import the Risk Log
1. Select Administration
2. Select Data Import

## Slide 86: Import the Risk Log
1 Select Risk (Project Data) from drop down
2 Browse for your CSV file
3 Select GTA Risk Fields Option

## Slide 87: Import Screen
1. Confirm Content
Select Import

## Slide 88: Import Confirmation
Select OK

## Slide 89: Check Import Activity
Current Risk Log Import Status
Completed Imports
NOTE: Selecting the magnifying glass will display reason for failed imports.

## Slide 90: View or Print Risk Log
1. Select Dashboards, APO
2. Select Risk Tab
3. Select Project
4. Right Click in Risk Log to copy, print or export.

## Slide 91: PM Monthly Updates
Use GEMS to Assess Project Health
Revise Project Assignments as Necessary
Schedule and Ensure Completion of Questionnaires
Update project (key project data or Profile Questionnaire)
Update Risk Log
Update Issues

## Slide 92: Printing Blank Questionnaires
1. Select Reporting
2. Select Questionnaire Details

## Slide 93: Select the Questionnaire
1. Select Project Data
2. Select the Questionnaire
3. Select Refresh
4. Dropdown, you can save as Excel, PDF or Word. PDF is best.

## Slide 94: Stage Gate Review Process
There are Two methods to Execute a Stage Gate Review
The PM manually initiates a Gate Questionnaire
The project moves into a new phase: (Next Slide)
Gate 1 > Design
Gate 2 > Develop
Gate 3 > Deploy
Gate 4 > Operate

## Slide 95: Stage Gate Review Process
PM Moves the Project to the Next Phase

## Slide 96: Monitor Project - Video

## Slide 97: Additional PM Monthly Updates
Update Project Schedule and Budget Data. Information can be keyed into the Project Data or loaded via the Project Profile Questionnaire.
  Planned Baseline Start Date
  Actual Start Date
  Planned Baseline Finish Date
  Actual Finish Date
  Percent Work Complete
  Baseline Effort
  Duration
  SPI
  Total Budget (State)
  Total Budget (Other Funds)
  Total Planned Expenditures
  Total Actual Expenditures
  Estimated Funds Needed to Complete

## Slide 98: Required Project Schedule Data
Summary data from your project plan is entered into GEMS
Baseline Start
Actual Start
Baseline Finish
Actual Finish
% Work Complete
Baseline Work
Duration
SPI

## Slide 99: Schedule & Budget Data Entry in GEMS
Fields Requiring Monthly Updates

## Slide 100: Scorecards and KPIs - Video

## Slide 101: Project Schedule Request
Dashboard Comments Questionnaire
Do NOT Attach File From Here
Specific Request

## Slide 102: Project Schedule - Attachments
Locate your project schedule via the Browse, change Description and Attachment name to reflect “GEMS Project Name & Date”, example, STARR 05.30.14.
Select “Add”
Select the Attachments tab
Select add attachment

## Slide 103: Monitor Questionnaire Responses
Remember – Questionnaires drive the dials.
You, as the PM, should monitor the responses to ensure there are no surprises.
The responses should be evaluated before you enter your monthly comments.

## Slide 104: Key Performance Indicators
Communication
Quality of communication, both upwards and downwards
Level of training for customers/users
Sufficiency of project status reporting to all stakeholders
Requirements defined and communicated well enough to move forward
Cost
Confidence that budget contingency amount is sufficient
Sustainability model that is defined and regularly reviewed
Project-to-date costs meeting expectations
Issue Management
Effectiveness of issue management occurring
Escalation path in place for all issues
Timely resolution of issues

## Slide 105: Key Performance Indicators
Quality
Acceptability of deliverables reviewed during last reporting period
Satisfaction with quality of work product to date
Success criteria well defined
Risk Management
Effectiveness of risk management occurring
Documented response strategies for risks
Level of risk carried by the project
Schedule
Confidence in viability of the schedule
Performance against the schedule (SPI)
Changes to schedule expectations
Submission of schedule into tool

## Slide 106: Reviewing Questionnaire Responses - Video

## Slide 107: Critical Panel Requirements
Revise Project Assignments as Necessary
Ensure Completion of Questionnaires
Update Risk Log
Update Issues
Update and Attach the Project Schedule
Update Project Data (Information can be keyed into the Project Data or loaded via the Project Profile Questionnaire)
Complete Dashboard Comments Questionnaire
Update Portfolio/Program Comments (if applicable)

## Slide 108: Critical Panel View
1. Select Critical Projects Tab
2. Select Project
3. Dials are driven by Questionnaires ONLY
250 Character Max
4. Six Month Trend
5. Comments Are Directly From Dashboard Comments Questionnaire

## Slide 109: Critical Panel Timeline (Approximate)
7 days
5 days
3 days
Review Answers and Identify Exceptions
Review results with Management (and IV&V if applicable)
CPR
Complete Comments Questionnaire
Ensure All Questionnaires are Answered
1 day
GTA Dashboard Due Date

## Slide 110: GEMS Quality Control
Sent monthly to the PM
Repeated errors are escalated to CIO, Agency Head
Checklist includes questionnaire respondent list
Schedule (.mpp) is also QC’d

## Slide 111: GEMS Quality Control
NOTE: If your project is not updated by the due date, the previous months CPR View will be included in the CPR binder with this disclaimer.
Disclaimer: This data was not updated

## Slide 112: Additional GEMS Training Resources
Online Help

## Slide 113: GEMS Training Videos
Select Help
All Videos are Available

## Slide 114: GTA EPMO GEMS Toolkit
Each agency will be provided a thumb drive containing the following:
    This PowerPoint Presentation
    Individual Training/Test Scripts
    Sample project plan
    Risk Logs in both .xls and .csv format
    Sample Business Case
    All videos linked to this presentation
    Information on how the scores are computed
    EPLC Process Maps
    Project Schedule and Budget updates to GEMS

## Slide 115: GEMS Support
Hank Oelze, hank.oelze@gta.ga.gov
        O: 404-463-5303
        C: 404-782-2743
Tometrice Strickland, tometrice.strickland@gta.ga.gov
        O:404.463.8474
        C: 404.207.0301

## Slide 116: Questions

## Slide 117: Portfolio/Program Comments
The following slides pertain to agencies that manage projects at a Program and/or Portfolio level and need to provide comments on each KPI on their respective dashboards.
Comments remain on your dashboard until you manually update the comments. For example, the Cost KPI dashboard dial displays within the green area in June and within the yellow area in July. Unless you manually change the comment before the Critical Panel review meeting, the comment will still reflect June’s KPI results.

## Slide 118: Creating a New Portfolio/Program
Select Projects
Select Portfolios

## Slide 119: Creating a New Portfolio/Program
Select add portfolio

## Slide 120: Creating a Static Portfolio/Program
Create Name
Short Description
Move Projects from Available to Included
Select Save
Select Static Portfolio
Select Active

## Slide 121: Adding Portfolio/Program Comments
Select Portfolio
Select KPI
Select Save
Enter Comments, (for Overall KPI, add as of date)
As of 12/31/13: Enter comments

## Slide 122: Portfolio/Program Comments
Select CPR View
Select Portfolio
Review Comments
Note As Of Date

## Slide 123: GEMS Support
Hank Oelze, hank.oelze@gta.ga.gov
        O: 404-463-5303
        C: 404-782-2743
Tometrice Strickland, tometrice.strickland@gta.ga.gov
        O:404.463.8474
        C: 404.207.0301