## Review Form
Focus Area | Questions to Consider | References | Assessment Golden | Assessment Roache | Assessment Jones | Assessment Smith | Assessment Milstead | Assessment (TBD) | Assessment Reilly | Average Score | Location (document page/section) | Reviewer Comments/Observations (Initials + comment to support your assessment selection) | Reviewer Recommendations (include reviewer initials)
|  |  | Select Preferred Assessment [at the Focus Area level] (Definitions for each drop-down selection can be found on the Data Table tab) | [6 empty] | For Use by Review Lead ONLY | Provide to support comments/observations | NOTE: Any scoring < 4 -Excellent, requires a supporting comment/observation. These should include the reviewer's initials and be written in such a way that they can be cut and pasted into the agency response letter (fit for external viewing) | It is not required that there be a one-to-one correlation between each observation and recommendation, but a clear linkage back to comments/observations is critical.
Problem Identification |  | Executive Summary Investment Purpose Alternatives Analysis
Does the problem appear to justify the cost and potential business changes required?
Has the agency attempted to address the problem through other means? (e.g. process adjustments, supplier negotiation, staff training, etc.)
Will the problem solution impact other entities (state and/or federal)? If so, have they been engaged in the discussions?
Does the Business Case effectively describe what success and/or failure looks like?
Does the Business Case clearly describe the problem or opportunity to be addressed from a business perspective
Does the business case show how this aligns with strategic goals?
Funding/Budget Considerations |  | Executive Summary Investment Purpose Alternatives Analysis
Are all funding sources identified? - State budget - Federal funds - Transactional Revenue Stream - Bonds - Other
Has all funding been approved/secured based on a Total Cost of Ownership (minimum of 5 years)? If not, will it be approved prior to initiating procurement?
Have unknown expenses been estimated (rough order of magnitude) and included in all relevant alternatives?
Has the agency considered costs of training for process redesign and/or technical skills associated with the proposed solution?
Can costs be tracked across all proposed alternatives?
Are there limitations on the funding that could impact the procurement and/or implementation strategies? If so, are these risks addressed?
Has the agency done a sufficient job of identifying all potential areas of cost associated with each alternative? - Staffing - Technical Solution (hardware and/or software) - Licenses - Maintenance and Support (initial and ongoing) - Software and/or Hardware services - Project Management resources - Consultants (OCM, IVV, BPR, etc.) - Data clean-up, recovery and/or migration
Procurement Strategy |  | Executive Summary Alternatives Analysis
Has a procurement strategy/strategies been proposed?
Are there procurement-specific risks or issues? (e.g. time constraints, solution availability, required sources, etc.)
Does Procurement Policy require DOAS involvement to move forward? Have they been engaged?
Investment Risks |  | Executive Summary Investment Purpose High Level Business Impact
Has the risk of "failure to act" been identified?
Has the Agency attempted to address all relevant risk areas? - Technology - Cost - Staff Impact - Political Ramifications - Customer/Client Impact - External agency/federal partner/supplier impacts -
Are the risks addressed in the analysis of each alternative?
Has the agency identified risk triggers that will be monitored during procurement and planning?
Are assumptions and constraints identified?
Investment Benefits |  | Executive Summary Alternatives Analysis Preferred Solution High Level Business Impact
Has the agency addressed all potential benefit areas? e.g.: - Financial - IT Security - Better availability of Resources for Maintenance/Ops - Improved Customer Service - Avoidance of penalties/censure - Improved data collection/analysis/reporting - Improved business processes
Are measurable goals established for possible benefits? (rough estimates are acceptable at this point in planning)
Are alternatives assessed based on how long it will take to realize benefits? If so, are there proposed timelines for achieving benefit realization? (FY, Calendar Year, Performance against current baseline, etc.)
Technical Viability |  | Executive Summary Alternatives Analysis Preferred Solution
Does the technical solution proposed take the State policies and standards into consideration?
Is the technology proposed consistent with current market standards and best practices?
Has the agency researched other government entities using the proposed solution?
Have a variety of technical options been considered? If so, what resources were used to obtain and evaluate those options?
Have you categorized the data that will be managed with the solution?
Based on the type of data managed, has the agency discussed appropriate security provisions in each of their proposed alternatives?
Alternatives Analysis |  | Executive Summary Alternatives Analysis Preferred Solution
Are all alternatives considered, including doing nothing?
Has the agency effectively addressed all costs associated with considered solutions? Do the costs represent a 5-year total cost of ownership?
For each alternative, has the agency documented the risks and benefits of each?
Are costs easily compared across the alternatives? Can the reviewer track each line item for all expenditures?
Are estimates provided for costs which may not be known at this time?
Does the document provide background on how the costs were derived? Can you easily understand what each cost represents?
Are assumptions and constraints identified in the analysis of each alternative?
Has benefit realization been included as part of the alternatives analysis? Can the reviewer identify which alternative will have the quickest and/or most successful return on investment?

## User Guide
Focus Area | Questions to Consider | References | Assessment Golden | Assessment Roache | Assessment Jones | Assessment Smith | Assessment Milstead | Assessment Reilly | Location (document page/section) | Reviewer Comments/Observations (Initials + comment to support your assessment selection) | Reviewer Recommendations (should clearly tie back to comments and observations)
Note: Scoring is done at the Focus Area level |  |  | Select Preferred Assessment
Contains key areas of review to assess the viability of the Business Case, as agreed upon by the EPMO team | A series of questions to assist the reviewer in evaluating the thoroughness of the agency’s response within each Focus Area | Reference to headings within the Business Case Form that may contain information in support of the Focus Area being reviewed |  | · Each reviewer will have their own Assessment Column (names will be inserted by the Review Team Lead prior to saving in the TEAMS folder for that Business Case |  |  |  |  | To be used by the reviewer to capture the location of any items they want to highlight (whether deficiencies or strengths in the case) | NOTE: If any score <4-Very Good is given by the reviewer, comments are mandatory to support selected score.
· Areas include: | It is not mandatory to score/evaluate each specific question; they are meant to provide guidance | These references are not all inclusive, but meant to assist the reviewer in filtering the provided information |  | · When using the form during the review, the reviewer may choose to hide the other review team members’ columns. This is a process decision for the team, just to make sure everyone has access to their section of the form. All other sections of the form are open for collaborative use. |  |  |  |  | Optional, not mandatory unless requested by the Review Team Lead
o Problem Identification
o Funding/Budget Considerations |  |  |  | · Within each Focus Area row there is a drop-down selection for the reviewer to assess how well the case has addressed that area. Drop-down options are: 0 - Did Not Address 1 - Poor 2 - Fair 3 - Good 4 - Very Good 5 - Excellent (Definitions can be found in the Data Table tab)
o Procurement Strategy
o Investment Risks
o Investment Benefits
o Technical Viability
o Alternatives Analysis
If the selection <4 - Very Good , the reviewer should enter supporting comments in the Reviewer Comments column (along with their initials for identification) and Recommendations, when appropriate.
- May be used as a means for organizing Business Case Reviews, e.g. GTA resources may only address one (or a few), rather than the entire scope of the document

## Data Table
Scoring Table Options | Definitions
0 Did not address | Provides no information to support the Focus Area or considered questions
1 Poor | Provides minimal information, but not sufficient for reviewer to assess effectively
2 Fair | Enough information to see that the writer understood the Focus Area purpose; answers some, but not all questions
3 Good | Focus Area is adequately addressed; provided answers to most questions; needs more clarity
4 Very Good | Exhibits a clear understanding of the justification required; provides strong answers to most questions
5 Excellent | Covered all aspects of the Focus Area well leading to clear support for the decision; no outstanding questions remain