## Cutover Plan
Cutover Planning (Templates)
Note: Most leading software vendors and systems integrators include similar concepts and tools in their methodologies.
If that is the case for your program, utilize this these spreadsheets (created from a combination of software vendor's methodologies)
as a checklist or guide to ensure that your cutover process is complete.
Use this list of tasks to validate that your cutover plan is complete. Your system integrator should plan a key role in creating a cutover plan for your specific project.
Cutover Plan
owner:
start date:
end date:
|  | Task | Owner | Dependency | Duration in hours | Planned Start Date | Planned End Date | Status | Signoff | Others involved
Getting started
1) | Prepare for Cutover
Finalize cutover plan and checklists
Communicate plan to cutover team
Communicate cutover timeline to the organization
Communicate go-live timeline to customers and vendors as appropriate
Plan and perform physical inventory
Implement configuration management plan
2) | Prepare Production Environment
Install production servers
Install the operation system and networking software
Connect the servers to the network
Create user accounts on the servers
Configure the file system on the servers
Configure printer drivers
Install the user machines and connect them to the network
Install the database on the database servers
Install the application servers
Configure the standard applications database objects
Create the custom database objects
Install the system management tools
Install printers and other peripheral devices
Secure access to the production environment
3) | Prepare User Learning Environment
See EUT Plan for details
4) | Set Up Applications
Set up the application users in the new system
Set up and compile the key flexfields
Enter the application setups
Load the initial setup data
Implement the security configuration
Register the application objects
Setup and compile the descriptive flexfields
Enter or load custom seed data
Verify the online operation of the applications
Verify batch operation of the operations
Back up the production system
5) | Install Conversion Programs
Install conversion programs and automated conversion tool software (if used)
List the location of each conversion program in the production environment
List the location of any conversion tools in the production environment
6) | Finalize System Administration
Ensure backups are running correctly
Ensure daily procedures in place
Ensure db has been allocated sufficiently
7) | Define Cutover Contingency Plan
Define contingency strategy
Determine contingency support staff
Determine contingency project team
Define users/management procedures
8) | Implement Production Support Infrastructure
See Help Desk Plan for details
9) | Conduct User Learning Events
See Help Desk Plan for details
10) | Perform Acceptance Test
Review responsibilities for the acceptance test with the team
Back up the production environment for later availability
Validate the acceptance test environment
Execute the acceptance test script
Document the results
Determine required actions for problem resolution
Make recommendations for application changes or corrections based on acceptance testing
Secure acceptance of acceptance test results
Final Cutover
1) | System and Network administration
Shut down legacy systems at appropriate time
Verify Printing/Faxing is working
Verify user Printing/Faxing defaults are set up
Ensure all network communications are in place
Ensure external access to system available
Ensure remote printers/services are available
2) | Convert and Verify Data
Verify legacy pre-conversion data cleanup has been completed
Describe the data conversion sequence
Sequence download programs
Sequence of interface table creation programs
Sequence upload programs
Sequence translation programs
Sequence interface/validation programs
Run the conversions (see Cutover Conversion Plan)
Enter manual conversions (see CutoverConversion Plan)
Verify the converted data (see Cutover Conversion Plan)
Secure acceptance that the converted and verified data meets century date compliance standards.
3) | Verify Production Readiness
Review the production readiness verification checklist
Conduct production readiness verification
Confirm the production cutover
Prepare the support team
Obtain agreement for the initial production schedule
Verify that users are trained
Verify commitment and readiness of internal and external support personnel
Verify the completion of the production environment
Confirm senior management commitment via the steering committee
Distribute the initial production schedule
Obtain approval for beginning production
4) | Begin Production
Initiate using the production system
Initiate incident/technical issue management procedures
Initiate open issues and create a resolution list
Initiate support
Confirm that all components of the production system are operational
Declare the new system live
EITK 0604

## Final Cutover Checklist
Note: Most leading software vendors and systems integrators include similar concepts and tools in their methodologies.
If that is the case for your program, utilize this these spreadsheets (created from a combination of software vendor's methodologies)
as a checklist or guide to ensure that your cutover process is complete.
Use this checklist/signoff as a final verification that you are ready to go live. Owners should be the lead for that area.
Final Cutover Checklist |  |  | Owner | Signoff | Date
Process Acceptance Complete
GL
|  | Integration Testing complete | PROJECT MANAGERS TO REVIEW AND CONFIRM |  |  | · Final user acceptance
|  | End user training complete | THIS CHECKLIST. IT WILL THEN BE DUPLICATED FOR |  |  | · Shutdown complete
|  | Procedures documents complete | EACH AREA. |  |  | · Conversion verification
|  | Documentation distributed |  |  |  | · Equipment verification
|  | Equipment ready |  |  |  | · Communications set up
|  | User accounts verified |  |  |  | · Technical verification
Conversions verified
Manual conversions complete
Communications established
Final system test accepted
|  | Help desk established |  |  |  | Final signoff
Legacy systems and input stopped
Final signoff
AR
Integration Testing complete
End user training complete
Procedures documents complete
Documentation distributed
Equipment ready
User accounts verified
Conversions verified
Manual conversions complete
Communications established
Final system test accepted
Help desk established
Legacy systems and input stopped
Final signoff
AR Order Fulfillment
Integration Testing complete
End user training complete
Procedures documents complete
Documentation distributed
Equipment ready
User accounts verified
Conversions verified
Manual conversions complete
Communications established
Final system test accepted
Help desk established
Legacy systems and input stopped
Final signoff
Contract Management
Funds Management
Inventory Management
Formula Management
| Quality Management |  | THIS SECTION TO BE COMPLETED
| Production / POC |  | SIMILAR TO THOSE ABOVE ONCE ALL
| Cost |  | STEPS FOR EACH AREA ARE CONFIRMED BY PMs
Order Fulfillment
MRP / MPS
Budgets
Accounts Payable
Purchasing
Fixed Assets
Inventory Management / Stores
Grants
AR (Grants & Endowment)
Projects (CPS)
Business Shutdown Complete
|  | Shipments | THIS SECTION TO BE COMPLETED
|  | A/P payments | FROM DETAILS PROVIDED BY EACH AREA
|  | A/R cash applied | ON THE CUTOVER PLANNING WORKSHEET
Production/ Inventory Reported
etc
etc
etc
Data Conversion
see Cutover Conversion Plan for detail
Equipment Set Up
System installed
System set up
Printers / faxes operational
Communications
Team members informed of Go / No-Go decision
Team members ready to GO
Help desk functioning
Issue tracking operational
Software vendor hot line aware of Go Live
Technical
Sufficient disk space
Sufficient memory
Production system verified
Legacy systems secured or shut off
Management signoff
SI Project Management
Client Project Manager
Client Program Manager
ABC Sponsors
ABC Sponsors
ABC Sponsors
ABC Sponsors
Note on C9: Update the list of process/application areas being implemented

## Cutover Contacts
Complete information for distribution and reference during cutover.
Insert rows for all functional/process areas in place of 'XX' place holder.
Cutover Team and Contact Information
Role | Function
Program Manager - | Provides management support - decisions, resources, direction
Project Manager - | Organizes detailed transition
Cutover Owner - | Leads the execution of the cutover plan
Migration Team Member - | Execute the detailed tasks
Technical Team Member - | Implement production environment and performs data conversions
Validation Team Member - | Responsible for final validation of prod'n environment just before go live
Role | Name | Hours | Phone # | Email | Beeper # | Location
Program Manager
Project Manager
Cutover Owner
GL Migration Team
GL Validation Team
GL Technical Team
AR Migration Team
AR Validation Team
AR Technical Team
XX Migration Team
XX Validation Team
XX Technical Team
Technical Team Member
Technical Team Member
Others:
Role | Name | Hours | Phone # | Email | Beeper # | Location
Executive
Project Sponsor
Project Sponsor
Project Sponsor
Project Sponsor
HR Manager
EUT Owner
Help Desk Owner (see also HD contacts)
Note on A15: List all cutover team members
Note on B15: Indicate the Cutover lead, team lead or power user responsible for each area
Note on C15: Indicate the hours the individual is scheduled to work. If a team member’s hour vary, insert additional lines and include the day or date with the relevant hours.
Note on D15: Indicate the phone number to be used during the specified hours.
Note on E15: Indicate the email address to be used during the specified hours.
Note on F15: Indicate the beeper number to be used during the specified hours.
Note on G15: Indicate the location the team member can be found for the hours specified.

## Cutover Issues Log
Note: Most leading software vendors and systems integrators include similar concepts and tools in their methodologies.
If that is the case for your program, utilize this these spreadsheets (created from a combination of software vendor's methodologies)
as a checklist or guide to ensure that your cutover process is complete.
Use this log as a sample of those components that should be tracked for issues that arise during cutover of tasks to step you through the converstion process. Many projects utilize the same
log or database used during the other phases of the project. Whether a formal database is in place or not, use this as a guide to assure your issue tracking meets the typical requirements.
Cutover Issue Log
Issue # | Initiator | Date Opened | Summary Description | Impact/ Importance | Type | Owner | Target Completion Date | Current Status | Completion Date | Resolution
1
2
3
4
5
….
Note on A10: sequential numbering of issues as they are logged works best
Note on B10: name of the initiator and their contact number
Note on C10: date and time stamp when the question or issue was raised (not the date it was logged in case there was a delay in logging it)
Note on D10: describe the question or issue in enough detail for others referencing the log to understand it
Note on E10: select prioritization of the issue based on its impact and importance: low – issue that needs to be addressed but does not impact going live or the timeline to complete the cutover tasks medium – does not prevent going live, but a work around may be needed and the cutover timeline may be impacted, therefore address promptly high – critical issue impacting both cutover and ability to go live, address immediately
Note on F10: select the nature of the issue from the list defined. Edit the list via Data --> Validation from the toolbar.
Note on G10: assign individual who is responsible for taking the next step to resolve the issue
Note on H10: date that resolution is targeted to be completed
Note on I10: indicates standing of the issue overall (not from the individual’s responsibility perspective)
Note on J10: when current status is updated to ‘closed’ indicate the date that it was resolved, documented and communicated
Note on K10: when current status is updated to ‘closed’ document the resolution defined