## Sheet1
Issue Number | Issue Description | Date Opened | Status | Priority | Assigned To | Escalate To | Date Resolved | Actions Taken | Days to Resolve | Resolved on Time | Days Open
1 | Issue 1 | 2011-03-01 | Open | High | Joe | Tom |  | mm/dd: action taken |  | No | 8
2 | Issue 2 | 2011-02-20 | Open | High | Bill | Al |  | mm/dd: action taken |  | No | 14
3 | Issue 3 | 2011-03-01 | Open | Low | Sally | Al |  | mm/dd: action taken |  | No | 8
4 | Issue 4 | 2011-02-01 | Open | Medium | Sam | Tom |  | mm/dd: action taken |  | No | 28
5 | [9 empty] | No | 0
6 | [9 empty] | No | 0
7 | [9 empty] | No | 0
8 | [9 empty] | No | 0
9 | [9 empty] | No | 0
[10 empty] | No | 0
| 4 | 2011-02-01 | 0 | 2 | 4 | 4 | 0 | 4 | 0 | 0 | 14.5
[9 empty] | 0 | 0 | 6.2069
| Number of Days Allowed Open | 90 | [6 empty] | 1 |  | 0.51786
| Number of Days to Resolve an Issue | 30 | [6 empty] | 0.75893
| Escalation Path for Issues | 5
| Resolved in Timely Manner | 3.7946
| Action Plans Exist for Issues | 5
| Percentage of High Priority Issues | 2.5
| Issues assigned an owner | 5
| Issue Score | 0.94
Formulas:
Days to Resolve = IF([Date Resolved]<>0,NETWORKDAYS([Date Opened],[Date Resolved]),"")
Days Open = IF(AND([Date Resolved]="",[Date Opened]<>""),NETWORKDAYS([Date Opened],[1]Tables!$B2),0)
Days Open = (L12/(NETWORKDAYS(C12,[1]Tables!$B2)))
Date Opened = MIN(C2:[Date Opened, row above])
Did not include the Pct of High Priority Issues score in the average.