## Checklist Guide
NOTE TO AUTHOR <The Readiness Checklist can be used throughout the project cycle to ensure that all activities necessary for a successful implementation and utilization have been sucessfully completed. It should be modified to include all relevant phases and/or stages of the project. The checklist can be incorporated into the project Communications plan as a tool for updating progress to stakeholders and team members. It is especially helpful when there are multiple streams of project activity being conducted in parallel (e.g. Design and Development; Organizational Change Management; Business Policy Redesign; etc.). The Readiness Checklist is most often used for cross-functional Stakeholder Groups to report comprehensive project status at the functional (not task or activity) level. Once the Critical Path items have been agreed to, success criteria (Column D) must be established so that there will be consistent agreement that the items have been completed. Rating criteria (Column J) should also defined as the checklist is developed and accepted by all key stakeholders. Because the checklist is designed to cover the entire scope and duration of the activities, some will not begin until much later in the project. It is desirable to distinguish between those that have not started because it is not yet appropriate and those that have not started because of delays (Column J). Health Score fields (Column I) have been formatted to change color based on the word entered in the field (Red, Yellow, Green). This formatting can be copied into other fields are required. The checklist is a sample and should be expanded or contracted to accommodate the scope and complexity of individual projects.>

## Initial
Critical Path Item |  |  | Success Criteria | Workaround/ Contingency Plan | Planned Start Date | Planned End Date | Responsible Party | Health Score | Rating Criteria | Comments/Corrective Action | Status
1-Issues | [7 empty] | Red | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
1.1 | Project Issues |  | All critical Steering Committee and High/Medium priority issues are closed or deferred. If the resolution changes the design, the design is complete and signed-off. | Assess each open issue on a case-by-case basis. Employ acceptable work around or contingency plan. |  |  |  | Green | Green = 0 issues or acceptable workarounds Red = 1+ Emergency or High |  | Completed
1.2 | Schedule Issues |  | -All critical Steering Committee and High/Medium priority issues are closed or deferred. If the resolution changes the design, the design is complete and signed-off. -Implementation strategy and timeline for Fleet and Surplus is documented and finalized | See Above |  |  |  | Red |  |  | In Progress - Behind Schedule
1.3 | Budget Issues |  | All critical Steering Committee and High/Medium priority issues are closed or deferred. If the resolution changes the design, the design is complete and signed-off. | See Above |  |  |  | Green | See Above | -Finalize hosting price with GTA -Provide budget documentation to Sherrie Southern | In Progress - On Schedule
1.4 | Business Objectives Issues |  | All critical Steering Committee and High/Medium priority issues are closed or deferred. If the resolution changes the design, the design is complete and signed-off. | See Above |  |  |  | Yellow | See Above | -Communicate/distribute Go-Live definition document (completed 2006/11/30) -Understand Stakeholder's expectations -Address next step/phase based on expectations | In Progress - On Schedule
1.5 | Organizational Readiness Issues |  | -All critical Steering Committee and High/Medium priority issues are closed or deferred. If the resolution changes the design, the design is complete and signed-off. | See Above |  |  |  | Red | See Above
1.6 | Tech/Security Issues |  | See Item 1.1 Above | See Above |  |  |  | Green | See Above |  | Completed
1.7 | Upgrade Issues |  | See Item 1.1 Above | See Above |  |  |  | Green | See Above |  | Completed
1.8 | Other Issues |  | See Item 1.1 Above | See Above |  |  |  | Green | See Above |  | Completed
2-Risks
2.1 |  | Project Risks | All critical risks are closed or mitigation strategies have been implemented. | [5 empty] | Yellow = no mitigation OR no work around. Red = do not have either mitigation or work around
2.1.1 | [8 empty] | See above
2.1.2 | [8 empty] | See above
2.1.3 | [8 empty] | See above
2.1.4 | [8 empty] | See above
2.1.5 | [8 empty] | See above
3-Application Readiness | [8 empty] | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
3.1 | Functional Test |  | -All functional scripts completed successfully; -Functional testing conducted in all environments; -Success criteria documented
3.2 | User Acceptance / Regression Testing (module 1) |  | -UAT agency testers identified and scheduled -UAT Test Scripts identified -Successful pass of all UAT Test Scripts -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects | Assess each function not successfully tested and determine if acceptable workaround can be employed |  |  |  | Red | Yellow = Medium without work around or low with no target completion date. Red = 1+ Emerg or High and/or less than 90% test cond passed | Business Owner must sign-off/accept UAT | In Progress - Behind Schedule
3.2.1
| User Acceptance / Regression Testing (module 2) |  | -UAT agency testers identified and scheduled -UAT Test Scripts identified -Successful pass of all UAT Test Scripts -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects | Same as above |  |  |  | Red |  | Business Owner must sign-off/accept UAT | Not Started - Behind Schedule
3.3 | Functions
|  | Workflow | -Workflow successfully tested -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects -Business Owner signed-off on application functionality |  |  |  |  | Green |  |  | In Progress - On Schedule
|  | Reports | -All Reports successfully completed -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects -Reports are ready for migration. -Business Owner signed-off on application functionality |  |  |  |  | Yellow |  |  | In Progress - On Schedule
|  | Screens | -All Screens developed -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects -Business Owner signed-off on application functionality |  |  |  |  | Green |  |  | In Progress - On Schedule
3.4 | Security |  | -100% of end-user security configured in X environment. -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects | [5 empty] | Yellow = Medium without work around or low with no target completion date. More than 1 in a module - Red OR <90% configured
3.4.1 | System Security Plan |  | -Security Plan developed and approved
3.8 | Defects |  | -No outstanding Severity Level 1 and/or 2 Defects -Workarounds in place for all Severity level 3 and/or 4 Defects -Target completion date identified for all level 3 and/or 4 Defects | Assess each Defect not successfully tested and determine if acceptable workaround can be employed |  |  |  |  | Yellow = Medium without work around or low with no target completion date. More than 1 in a module - Red
3.9 | Decommission Legacy System(s) |  | -List of decommission apps/ functions completed and approved -Agreement with legacy vendor in place -Migration procedures created -Legacy environment shut down -Backups of legacy systems taken
4-Technical Infrastructure Readiness | [7 empty] | Green | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
4.1 | Hardware
4.1.1 |  | Web Servers | -Production servers installed, tested, and stable -Production servers available during scheduled hours |  |  |  |  | Green | Green = Pass Yellow = at Risk - list reasons Red = Fail |  | Completed
4.1.2 |  | Application Servers | -Application servers installed, tested, and stable -Application servers available during scheduled hours |  |  |  |  | Green | See Above |  | Completed
4.1.3 |  | Infrastructure Hosting | -Operational Readiness Checklist complete and accepted by Business Owner; -System performance meets success metrics; -Final configuration documented and changes to CSP accepted by Business Owner/CIO
4.2 | Software
4.2.1 |  | Additional Software | All required additional software identified, installed and tested |  |  |  |  | Yellow | See Above |  | In Progress - On Schedule
4.2.2 |  | Patches & Fixes | -Software patched to most current version - Post production patches and/or fixes scheduled |  |  |  |  | Green | See Above |  | Completed
5-Third Party Readiness | [7 empty] | Red | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
5.1 | Inbound Interfaces (may need to add sections for Outbound as well)
5.1.1 |  |  | 1 - Technical Test Complete 2 - Functional Test Complete 3 - Third Party Confirmation Received 4 - Rollback procedures and communications prepared and discussed |  |  |  |  | Red | - X tests conducted successfully - sign-off from external partner - fewer than X data errors |  | In Progress - Behind Schedule
5.1.1.1 |  |  | MOU executed between ___ and ___ for ongoing maintenance and support issues
5.1.2 |  |  | 1 - Technical Test Complete 2 - Functional Test Complete 3 - Third Party Confirmation Received 4 - Rollback procedures and communications prepared and discussed |  |  |  |  | Red | See Above |  | In Progress - Behind Schedule
5.1.2.1 |  |  | MOU executed between ___ and ___ for ongoing maintenance and support issues
5.2 | Overall Connectivity |  | 1 - Connectivity to 3rd parties established | N/A |  |  |  | Green | See Above |  | Completed
6-Training | [8 empty] | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
6.1 | Training |  | -Training Fixes completed for on-line materials; -SME review completed -Published and available online -End Users Identified -Communications sent to end users -Surveys completed |  |  |  |  | Yellow | Yellow = Survey results unclear Red = sessions not executed or survey results show dissatisfaction |  | In Progress - Behind Schedule
6.1.1 |  | Instructor-Led Training | -Document and Accept the training approach. - Training scheduled; - Training conducted; - X% of students successfully utilizing application (or passed course test, etc.) | Conduct make-up training sessions post go-live |  |  |  | Red | Yellow = Survey results unclear or 80 - 90% key users attended Red = <80% key users attended or sessions not executed or survey results show dissatisfaction
6.3 | Ongoing Training Support |  | -Responsibility for support assigned -Handoff conducted
7-Operational Readiness | [8 empty] | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
7.1 | Operations Test
7.1.1 |  | Help Desk | -Help Desk Staff have been identified and trained -Knowledge Transfer plans completed and scheduled for sign-off -Help desk tools identified and in-place -Transition date from temporary to full-time staff set | Project team to provide support on temporary basis |  |  |  | Red | Green = Pass Yellow = at Risk - list reasons Red = Fail |  | In Progress - Behind Schedule
7.1.1.1 |  | GETS Help Desk (if applicable) | -Instructions have been provided to GETS Help Desk personnel; -Excalation processes defined and documented; -
7.1.2 |  | System Supportability | -Documentation exists for systems operations, maintenance, and support -Application support staff trained -Staff can operate and maintain system -Processes are in place for new development and configuration change requests -Schedules for delivered patches and fixes are in place |  |  |  |  | Red | See Above
7.1.3 |  | System Recoverability | -Documentation exists for back-up, recovery, and error procedures -Areas that encounter errors have been documented -The infrastructure is recoverable and the staff has adequately performed and tested the procedure X times |  |  |  |  | Red | See Above
7.2 | System Administration |  | -Admin role and responsibility documented; -Admin(s) assigned; -User coordinators trained; -New user processes documented and communicated |  |  |  |  | Yellow
7.3 | Deployment Test
7.3.1 |  | Deployment Plan | A detailed deployment plan has been documented, communicated and activities scheduled | N/A |  |  |  |  | See Above
7.3.2 |  | Test Moves to Production | -Minimum of X test moves have been conducted -Upgraded environment adequately tested -Last Test Move (including all upgrade deployment activities) completed in X days or less -Deployment tasks timed and migration calendar prepared | Increase go-live window |  |  |  |  | See Above
7.3.3 |  | Ready for Final Move to Production | -Technical staff required on site or remote access identified and scheduled -Functional staff required on site or remote access identified and scheduled -Communication procedures and on-call roster developed and communicated -Facilities and equipment available for upgrade weekend(s) (no power or equipment outages scheduled) |  |  |  |  | Red | See Above
7.3.4 |  | Configuration | -Configuration items complete -Migration scripts prepared and adequately tested -Manual configuration tasks identified and timing known | N/A |  |  |  |  | See Above
7.3.5 |  | Security | -Security set-up complete -Migration scripts prepared and adequately tested -Manual security tasks identified and timing known | N/A |  |  |  |  | See Above
7.3.6 |  | Data Conversion | -Scrub of data complete and accepted by Business Owner -Migration scripts prepared and adequately tested (X times) -Manual conversion tasks identified and timing known -Record rejects process defined and ownership assigned
7.3.7 |  | Data Archival | -Archival strategy for production environment complete and sign-off obtained
7.4 | Deployment Verification Test
7.4.1 |  | System | - | N/A |  |  |  |  | See Above
7.4.2 |  | Configuration / Set up | -Interfaces are installed -Configurations are migrated -Development objects are migrated -Security is migrated / set up | N/A |  |  |  |  | See Above
7.4.3 |  | Functionality | -Identify transactions to be entered using live production data -Interfaces function properly -Configurations function properly -Development objects function properly -Security functions properly | N/A |  |  |  |  | See Above
7.4.4 |  | Data | -Conversions are complete -Data is reconciled | Determine which, if any, conversions can be performed after go-live. |  |  |  |  | See Above
8-Organizational Readiness | [8 empty] | 1+ Red = Red 0 Red but 1+ Yellow = Yellow
8.1 | Agencies/End Users
8.1.1 |  | Policies and Procedures | -Policies and procedures defined, documented and communicated -New policies are incorporated into training | N/A |  |  |  |  | Green = Pass Yellow = at Risk - list reasons Red = Fail
8.1.2 |  | User Readiness Assessment | -All application and customer support personnel in place; -Communications plan executed; -End-user groups established; -Contingency strategies in place for user issues | N/A |  |  |  |  | Yellow = 75 - 85% sign-off Red = <75%
8.1.3 |  | After go-live Stabilization Meetings | -Schedule after go-live stabilization check-in meetings -Set up bridge line -Communicate to Users logistics | N/A |  |  |  |  | Green = Pass Yellow = at Risk - list reasons Red = Fail
8.2 | Functional Hand-off Meetings |  | All Functional hand-off meetings have occurred
8.3 | Communications
8.3.1 |  | Executive Communications | Communications prepared for Identified stakeholders regarding project/go-live: -1 month prior to go-live -2 weeks prior to go-live -Day before go-live -Go-live day | N/A |  |  |  |  | See Above
8.3.2 |  | End User Communications | Communications and procedures for enforcing freezes are complete (i.e., new vendors, PO's, Chartfield values, vouchers, development). | N/A |  |  |  |  | See Above
8.3.3 |  | External Communications | 3rd Party interface owners (internal and external) notified of schedule | N/A |  |  |  |  | See Above
8.4 | Data Exception Process |  | FSS staff provided exception handling procedures
8.5 | Go-Live Contingency Plan
8.5.1 |  | Organizational Budgets | -Contract costs for extending legacy defined; -Extension of implementation vendor calculated; -Other cost impacts defined | N/A |  |  |  |  | See Above
8.5.2 |  | Interfaces |  | N/A |  |  |  |  | See Above
8.5.3 |  | Communications | Go-No-Go communications prepared for all impacted audiences (Project Team, Agencies, External Users, etc.) | N/A |  |  |  |  | See Above
Overall | [8 empty] | Green = go forward with upgrade; Red = cease upgrade

## Values
Status
Not Started - On Schedule
Not Started - Behind Schedule
In Progress - On Schedule
In Progress - Behind Schedule
Completed