[Insert Agency’s Name and Logo]

Statement of Work for

[Insert project name]

[Date]

Document Control Sheet

General Information

| Project Name | Project Manager | Business Owner (Key Sponsor) | Provider Single Point of Contact |
| --- | --- | --- | --- |

Document Preparation Information

| Author |  | Date | Organization Name |
| --- | --- | --- | --- |
| Phone Number |  | E-Mail |  |
| File Location (link) |  |  |  |

Distribution and Approvals

| Name | Title and Organization | Signature | Approval Date |
| --- | --- | --- | --- |

Change History

| Date | Change Description | Approved By |
| --- | --- | --- |

Guidelines and Instructions

(Note: Delete this guidelines and instructions section upon completion of the SOW.)

Overview

IT projects often fail because the parties involved don’t fully understand what work needs to be done or how success will be measured. Companies can mitigate this risk through the creation of a solid Statement of Work (SOW) document.

According to the PMBOK from the Project Management Institute (PMI) the SOW, also called statement of requirements (SOR), is “a narrative description of `product, services, or results to be supplied under contract.” In the PMBOK, the SOW is part of the project procurement management process. The SOW is used to set the scope and boundaries of a project and to establish an agreement between the company and an external provider about what work will be done, when it will performed, and who will do it.

Key Components

The SOW identifies:

- The project’s high level goals, objectives, dependencies, and constraints.

- The scope of the work associated with the project.

- Project deliverables and acceptance criteria.

- What work will be performed, who is responsible the work, when it will be finished. The SOW does not describe how the work will be accomplished.

Accountability

The project manager is responsible for creating and updating the SOW.

Inputs

The following project management documents must be completed before preparing the SOW:

- Business Case.

- Business Requirements.

- Work Breakdown Structure (WBS)

- Project plan.

- Project charter.

- Change management plan.

- Communications plan.

- Staffing plan

Tips

- Make sure that the people in the distribution list understand that by signing this document, they are formally accepting this as scope of the project. Allow two business days for people in the distribution list to review and approve the SOW.

- Once the SOW is approved, attach it to the contract, give copies to the project team, and file an original signed copy in the project binder.

- As the work gets underway, revisit this document at regular reporting intervals. Make changes as necessary, but make sure that all the approvers sign to recognize and acknowledge changes.

- Don’t make assumptions in the SOW because they are passive and can lead to misinterpretations. Transform assumptions into any of these:

  - A tangible scope statement (either inclusive or exclusive).

  - A new acceptance criterion for a specific deliverable.

  - A new entry in the risk management plan.

  - A new entry in the roles and responsibility matrix.

- The SOW must be written in language understandable to all parties involved in the project. Don’t use internal terminology unless this is an exclusively internal project.

SOW versus Other Project Management Documents

Companies often use interchangeably certain project management documents such as the SOW, contract, project charter, RFP, and letter of approval. While there are similarities between these documents, they serve different purposes and must be used in different circumstances.

| Project management document | Difference with SOW |
| --- | --- |
| Contract - According to the PMBOK a project charter is “a mutually binding agreement that obligates the seller to provide the specified product or service or result and obligates the buyer to pay for it.” | The SOW usually doesn’t replace a contract but complements it. The contract must mention the SOW as the document that describes in detail the work that will be performed. Other aspects of the agreement such as pricing, payment terms, payment schedules, and special clauses are usually described in the contract unless one of the following: - The SOW will be used as the contract. If this is the case, the company must make sure the SOW is properly reviewed by the legal department. - There is a master contract that will be used for multiple project phases or deliverables. For each phase, there will be a SOW that describes all the details relevant to the phase. |
| Project charter - According to the PMBOK a project charter is “a document issued by the project initiator or sponsor that formally authorizes the existence of a project, and provides the project manager with the authority to apply organizational resources to project activities.” | There are two essential differences: - The project charter establishes agreement between the sponsors and the project manager/project team. The SOW establishes agreement between the company and a provider. - The project charter is an internal document that describes both the internal and external project components. The SOW, on the other hand, is a document that is used to describe only the external project components. When the project doesn’t have an external component, companies should only use the project charter to specify the work to be done. |
| Request for Proposal (RFP) - The RFP states the project requirements in a way that third parties can propose how they will accomplish the tasks and satisfy the requirements of the project. | The RFP is usually utilized prior to the SOW. The RFP is used to solicit proposals from prospective providers. Once the enterprise selects a single provider, a formal SOW is issued to establish agreement between the enterprise and the vendor on exactly what work will be performed. |
| Letter of Agreement (LOA) - Also known as a letter of understanding, memorandum of understanding, or a scope of work agreement, a LOA is a brief document that summarizes basic items of agreement between the enterprise and an external provider. In comparison with a SOW, a LOA is much briefer, making it faster and easier to draft. | The LOA replaces the SOW in the following situations: - Small engagements where a full SOW and contract would be overkill. - Projects where work must begin so quickly that there is no time to draft a contract. - As a pre-contract where project details or the suitability of an external provider are not yet known and committing to a full contract would be premature or unwise. - Work agreements or schedules where a master contract has already been signed and the external provider is continuously re-engaged for short, iterative assignments. |

Table of Contents

1	Background	7

2	Project Objectives	7

3	Scope	7

3.1	Included	7

3.2	Excluded	7

4	Deliverables	8

5	Major Milestones	9

6	Company Commitments	9

7	Change Management	10

8	Project Reporting and Communication	10

9	Roles and Responsibilities	11

# Background

Provide some background and relevant history that explains what initiated this project.

Source(s) of information: Business case.

# Project Objectives

Describe the business drivers and state the high level goals for this project. Identify dependencies and constraints (e.g. the project must go live by a specific date because a new legislation will be in effect).

Source(s) of information: Business case.

# Scope

This section sets the boundaries for the project and describes exactly the products and services that are under contract. Be specific in the scope definition. Make sure that each requirement definition meets the SMART rule: must be specific, measurable, achievable, realistic, and time oriented. If required, embed any product specifications documents in this section.

Source(s) of information: Business requirements, WBS, project plan.

## Included

Use this sub-section to clearly define what the project will do. Be specific and include all the necessary details to provide a complete and unambiguous description of the project scope.

| Requirement | Agreed Solution |
| --- | --- |

## Excluded

Use this sub-section to clearly define what is out of the scope of this project.

# Deliverables

List here all the major deliverables and tangible outcomes of the project. These usually correspond to the major project activities described in the WBS. For each deliverable, establish concrete acceptance criteria, identify the person responsible for accepting the deliverable, and include the delivery date agreed upon with the provider.

Source(s) of information: WBS, project plan.

| Deliverable | Responsible | Acceptance Criteria | Due Date | Approver |
| --- | --- | --- | --- | --- |

# Major Milestones

List here key project milestones, task owner, and target dates agreed upon with the provider.

Source(s) of information: WBS, project plan.

| Milestone | Responsible | Target Begin Date | Target End Date |
| --- | --- | --- | --- |

# Company Commitments

Describe in this section the tasks (e.g. user testing), resources (e.g. people, computers, offices), and deliverables (e.g. sample data) that the company has agreed to deliver to the provider for a successful project execution.

Source(s) of information: WBS, project plan, project charter.

| Commitment | Responsible | Target Begin Date | Target End Date |
| --- | --- | --- | --- |

# Change Control

As the project progresses it may be necessary to amend the SOW. Explain in this section the change control process that any SOW changes must follow to be either approved or rejected. Changes must be acknowledged and signed by all stakeholders in the SOW distribution list.

Source(s) of information: change management plan.

# Project Reporting and Communication

Describe the communication approach that will be used between the company and the provider during the duration of the project.  This includes:

- Communication method (e.g. status reports, steering committee meetings, reviews).

- Communication frequency (e.g. weekly, monthly).

- Mechanisms for problem resolution and issue escalation.

Source(s) of information: communications plan.

# Roles and Responsibilities

Describe the roles and responsibilities that are relevant to the portion of the project that will be delivered by the provider.

Source(s) of information: staffing plan.

| Role | Name | Organization | Responsibilities | Time to the Project |
| --- | --- | --- | --- | --- |

__________________________________________________