## Slide 1: Principles of Effective Portfolio Management
George D. Starr
Sr. Director, PPM Practice
CA
Welcome

## Slide 2
George D. Starr is a Sr. Director at CA in the Project and Portfolio Management services practice. In his career he has worked with over 200 corporations to help them understand and improve PPM maturity, processes, competencies, and technology.
George has served as a professional services and software development leader at several other software companies over his 20 year career including Serena Software, Pacific Edge, UPS, and EXE (now Infor).
He holds a B.S. degree from Florida A&M University and M.S. from Florida State University, both in Mathematics. George has been a proud resident of Georgia and the metro-Atlanta area since 2003.
Presenter Bio

## Slide 3
Establishing Portfolio Standards
How do you decide where to invest your organization’s time, budget and staff? On what do you base your decision to expand delivery of a service or develop an innovation?
Defining your Strategic Portfolio
Once you’ve determined how best to measure your portfolio against your strategic goals, you can inventory current and proposed projects and evaluate them against the selected criteria.
Evaluating Your Portfolio
This is the step where one can perform critical what-if scenario planning that can empower your agency to make smarter portfolio decisions about investment mix, project selection, timing, execution, sourcing, performance and anticipated outcomes.
Improving Portfolio Performance
Your portfolio will never be static. Demands change, as do budgets and revenue requirements. You must be able to answer the really important questions: Is my portfolio in alignment with strategic business goals? How should I invest my limited resources?
Introduction
What are the essential processes in portfolio management? Why is it becoming more important today?
Topics

## Slide 4
Topics
Introduction to Portfolio Management Processes
Establishing Portfolio Standards
Defining your Strategic Portfolio
Evaluating Your Portfolio
Improving Portfolio Performance

## Slide 5
Gathering candidate ideas for investment from various sources (internal and external)
Considering candidate and approved projects based upon an analytic decision making framework
Choosing highly ranked projects that together meet constraints for budget and resources.
Reporting on changes, progress, and results in the portfolio
Reconsidering the portfolio on an ongoing basis
Practicing continuous improvement of Portfolio Management processes.
What is Portfolio Management?

## Slide 6
Identification
Categorization
Elaboration
Evaluation
Prioritization
Selection
Reporting
Improvement
Eight key processes are involved in choosing the right Portfolio

## Slide 7
Processes | Description | Best & Emerging Practices | Enablers
1. Identification | A process for gathering and submitting ideas for evaluation | Crowd sourcing A2A/B2B relationship managers | People Process Owners Clear Roles & Responsibilities Training Easy Access to Processes, Standards, Metrics and Results Process Continuous Planning Data Standards Minimum Criteria SLOs Metrics Simplicity Technology Centralized Data Automation Analytics Auditability Reporting & Visibility
2. Categorization | A process for categorization of ideas to determine what process will be used for evaluation, e.g. mandatory vs. discretionary, major vs. minor, etc. | Classification Standards | 
3. Elaboration | A process for elaboration of ideas into Concept or Business Cases that include collection and analysis of information such as descriptive data, benefits, costs, strategic alignment, and risk | Standard Concept/Business Cases Revision of Concept/Business Cases for Approved/Active projects Relative Estimation | 
4. Evaluation | A process for evaluating concepts/business cases and approved/active projects for value, risk, strategic alignment as well the identification of similar/alternative projects | Scoring Models Re-evaluation of approved/active projects Secondary/independent evaluation | 
5. Prioritization | Prioritizing candidate and current projects through data driven analysis of value, risk, strategic alignment and similar/alternate projects | Scoring Models | 
6. Selection | Determining which projects or projects will be implemented (postponed or canceled) by considering priorities and resource constraints (people and financial) | Demand vs. Capacity Optimization Scenario Planning | 
7. Reporting | Communicating portfolio results & changes (i.e. new projects, postponed projects, and canceled projects) | Executive Reports & Dashboards Customer Feedback | 
8. Improvement | Capturing portfolio management metrics, evaluate portfolio performance, capture lessons learned, gather feedback, and refine portfolio management processes | Communicate SLOs and Metrics Communicate Portfolio Results and Trends Benchmarking Surveys | 
Eight key processes are involved in choosing the right Portfolio

## Slide 8
What makes Portfolio Management even more relevant today?
Changing environment of Federal regulation and policy across commercial and social services (such as healthcare reform)
Rising expectations for self-service and customer service due to digitization
Changes in economy, populations, property values, employment, and income levels impact local, state, and federal revenues
Change requires Agility to consider, decide, execute, and reconsider project and spending decisions

## Slide 9
Topics
Introduction to Portfolio Management Processes
Establishing Portfolio Standards
Defining your Strategic Portfolio
Evaluating Your Portfolio
Improving Portfolio Performance

## Slide 10
Establishing Portfolio Standards
  Portfolio Management depends upon standards that must be established for the data, measures, scores, and criteria involved in each portfolio management process.
Data
Measures
Scores
Criteria

## Slide 11
Processes | Description | Best & Emerging Practices | Enablers
1. Identification | A process for gathering and submitting ideas for evaluation | Crowd sourcing A2A/B2B relationship managers | People Process Owners Clear Roles & Responsibilities Training Easy Access to Processes, Standards, Metrics and Results Process Continuous Processes Data Standards Minimum Criteria SLOs Metrics Simplicity Technology Centralized Data Automation Analytics Auditability Reporting & Visibility
2. Categorization | A process for categorization of ideas to determine what process will be used for evaluation, e.g. mandatory vs. discretionary, major vs. minor, etc. | Classification Standards | 
3. Elaboration | A process for elaboration of ideas into Concept or Business Cases that include collection and analysis of information such as descriptive data, benefits, costs, strategic alignment, and risk | Standard Concept/Business Cases Revision of Concept/Business Cases for Approved/Active projects Relative Estimation | 
4. Evaluation | A process for evaluating concepts/business cases and approved/active projects for value, risk, strategic alignment as well the identification of similar/alternative projects | Scoring Models Re-evaluation of approved/active projects Secondary/independent evaluation | 
5. Prioritization | Prioritizing candidate and current projects through data driven analysis of value, risk, strategic alignment and similar/alternate projects | Scoring Models | 
6. Selection | Determining which projects or projects will be implemented (postponed or canceled) by considering priorities and resource constraints (people and financial) | Demand vs. Capacity Optimization Scenario Planning | 
7. Reporting | Communicating portfolio results & changes (i.e. new projects, postponed projects, and canceled projects) | Executive Reports & Dashboards Customer Feedback | 
8. Improvement | Capturing portfolio management metrics, evaluate portfolio performance, capture lessons learned, gather feedback, and refine portfolio management processes | Communicate SLOs and Metrics Communicate Portfolio Results and Trends Benchmarking Surveys | 
Standards play an essential role in Categorization to Selection

## Slide 12
New Data
Criteria
Scores
Measures
Categorization
Ideas
Description
Source
Priority
Subject
Imperative vs. Discretionary vs. Innovation
Popularity
Max. number of ideas
Completeness and clarity
Min. popularity
Min. priority
Financial (NPV, ROI)
KPIs (Service Levels, etc.)
Elaboration
Benefits
Revenue
Cost
Risks
Strategy/Goal Relationships
Max. number of ideas
Completeness and clarity
Min. estimated impact (Financial measures or KPIs)
Evaluation
Value
Risk
Strategic Alignment
Overall score/rank
Max. number of ideas
Completeness and clarity
Min. estimated impact (Financial measures or KPIs)
Min. scores
Portfolio Financials
Selection
Max. no. of projects
Constrained by budget
Constrained by resources
Consideration of risk and alternatives
Approved projects
Cancelled or Postponed projects
Unapproved projects
Portfolio outcomes
Standards are defined for each Portfolio Management Process

## Slide 13
Topics
Introduction to Portfolio Management Processes
Establishing Portfolio Standards
Defining your Strategic Portfolio
Evaluating Your Portfolio
Improving Portfolio Performance

## Slide 14
Customers
Research
Policy & Law
Strategic Portfolio
The most common metaphor for Building a Portfolio is a “Funnel”
Internal
Audit
Other
Identification
Categorization
Evaluation
Selection
  Ideas come from various sources. All such demand must go through several processes to make it into the Strategic Portfolio. At each stage criteria or analysis is applied to determine which ideas make it to the next step.
Portfolio Management

## Slide 15
What are the Processes and Best Practices for Building the Portfolio?
Processes | Description | Best & Emerging Practices
1. Identification | A process for gathering and submitting ideas for evaluation | Crowd sourcing A2A/B2B relationship managers
2. Categorization | A process for categorization of ideas to determine what process will be used for evaluation, e.g. mandatory vs. discretionary, major vs. minor, etc. | Classification Standards
3. Elaboration | A process for elaboration of ideas into Concept or Business Cases that include collection and analysis of information such as descriptive data, benefits, costs, strategic alignment, and risk | Standard Concept/Business Cases Revision of Concept/Business Cases for Approved/Active projects Relative Estimation
4. Evaluation | A process for evaluating concepts/business cases and approved/active projects for value, risk, strategic alignment as well the identification of similar/alternative projects | Scoring Models Re-evaluation of approved/active projects Secondary/independent evaluation
5. Prioritization | Prioritizing candidate and current projects through data driven analysis of value, risk, strategic alignment and similar/alternate projects | Scoring Models

## Slide 16
Identification
Categorization
Elaboration
Evaluation
Prioritization
Demand Sources
Portfolio Processes
Demand from all sources enters the portfolio through Identification
Customers
Policy & Law
Research
Internal
Vendors
Audit

## Slide 17
Identification
Categorization
Elaboration
Evaluation
Prioritization
Demand Sources
Customers
Policy & Law
Research
Internal
Vendors
Demand Processes
Approved projects are also considered when Building a Portfolio
Audit
Approved projects
Approved projects must be included in the process. This links Portfolio Management to Project & Program Management, because the latter is the source for the required data on Approved projects.

## Slide 18
Provides a means to gather ideas (crowd sourcing) or submit ideas
Automates the workflow of ideas through processes by routing them to the right people and tracking cycle times to identify bottlenecks
Enforces standards throughout the process
Performs calculations for measures and scores
Provides data on active (or approved) projects and resource capacity/availability
Provides analytic support for considering multiple ideas and project simultaneously
Provides reporting and transparency to process participants, stakeholders, or even constituents
The role of technology in Building a Strategic Portfolio

## Slide 19
Topics
Introduction to Portfolio Management Processes
Establishing Portfolio Standards
Defining your Strategic Portfolio
Evaluating Your Portfolio
Improving Portfolio Performance

## Slide 20
Projects
Schedule
Cost
Resources
Constraints
Budgets
Resources
How do you determine which projects will make the list?
  Planning requires consideration of projects and constraints to arrive at a viable portfolio for the enterprise.

## Slide 21
“Waterlines” show what can be accomplished from the Prioritized List
  “Waterlines” provide a graphical way to see “how far down the list you can go” and “what is required to go further” (i.e. resources or budget)

## Slide 22
“What if” analysis enables rapid re-evaluation of the Portfolio
Which projects could we accomplish with more or less?
Which projects can we accomplish now?
We Change the Projects
Add/Remove
+/- Cost
We Change the Constraints
+/- Resources
+/- Budget
Change Schedule
+/- Resources
+/- Priority
  No portfolio planning exercise ends in one “pass”. Multiple iterations are required to consider “how can we get more done”, “what if we shift a project’s schedule”, “what if we increase/decrease the budget”, and “what if we increase/decrease resources”?

## Slide 23
Provides “waterline” analysis
Provides “what if” scenarios
Enables rapid evaluation if changes are made to the underlying projects, budgets, or resources
The role of technology in Evaluating Your Portfolio

## Slide 24
Topics
Introduction to Portfolio Management Processes
Establishing Portfolio Standards
Defining your Strategic Portfolio
Evaluating Your Portfolio
Improving Portfolio Performance

## Slide 25
Make Decisions with Data
Gather ideas internally and externally
Manage Projects Effectively
Improve project and program management methods, processes, and competencies
Encourage transparency in project performance and risk
Track benefits realization for approved projects
Plan More Often
Make Portfolio Management a continuous process
Make Changes
Re-evaluate the cost, risk, benefits, and alignment of approved projects
Consider higher-value or lower risk alternatives
Encourage the behavior to say “no” or “stop” if a project is not a good fit in the portfolio
It is not just an annual event
Select the right projects using standards and data
Improving portfolio performance is largely based upon effective project delivery and the ability to make changes
  You cannot assume that approved projects will achieve the initially expected results. Their value, risk, and cost must be periodically re-evaluated. If projects are underperforming or have better alternatives, they should be cancelled or replaced.

## Slide 26
Portfolio Management
Financial Management
Resource Management
Project and Program Management
Status
Performance
Risk
Capacity
Availability
Budgets
Forecasts
Actuals
Benefits
Effective Portfolio Management depends on other processes
  Timely and accurate information from Project Management, Resource Management, and Portfolio Management processes are required to make effective Portfolio decisions.
Decisions
Approvals
Changes

## Slide 27
Provides timely and accurate data from other processes such as project, resource, and financial management
Enables identification of underperforming projects
Reduces the effort and shortens the duration for portfolio management activities to enable “continuous planning”
Provides analytic support for considering multiple ideas and project simultaneously
Enables faster re-planning when budgets change or new projects are mandated/required
Provides reporting and transparency to process participants, stakeholders, or even constituents
The role of technology in Improving Portfolio Performance

## Slide 28: Principles of Effective Portfolio Management
George D. Starr
Sr. Director, PPM Practice
CA
Q&A