## Instructions
How to use this tool kit
This tool is based on the PMI® PM Competency Development Framework. It will allow the project manager a means to assess his/her competency in project
management as it relates to knowledge, performance, and personal attributes.
Before performing an assessment familiarize yourself with each section of the tool kit. The worksheets entitled Initiating,
Planning, Executing, Monitoring, and Closing describe competencies for project knowledge and performance in detail. The worksheets entitled
Communicating, Leading, Managing, Cognitive, Effectiveness, and Professionalism describe competencies for behaviors and attitudes. The last
worksheet contains the aggregate ratings from each assessment area and determines a final rating. You will notice the font color of several items is red.
These items are not required to be assessed. The rating is selected from the drop down list for each item. Valid values are Exceeds, Meets, Below, NA, or blank.
Each rating is given a value of blank, 5, 3, blank, and 0 respectively. A blank rating will result in a value of 0. These values are then averaged for the sheet and
displayed. If any item does not pertain to you at this time you may assess it with an NA and the value does not affect the score. Items in red should be
assessed as NA. If a 'Type of Evidence' has multiple items and a combination of red and black items, only assess the items in black.
To start the assessment, select a worksheet and using the rating scale provided assess your knowledge and performance competency for each element.
You will then see the results of the assessment for that element. Continue to the next worksheet and repeat the process until you complete ALL worksheets.
Scores on the Totals worksheet can now be used to assist the project manager identify competency gaps (Below), improvement opportunities (Meets),
and strengths to leverage (Exceeds). It is recommended that the project manager choose one strength to further develop and leverage, and two gaps
or opportunities where competency can be developed. Once these items are selected, development activities can be planned to either increase
knowledge or performance for the selected competency.
It is recommended that the project manager re-assess these selected elements periodically to observe progress toward achieving the desired
level of competency.

## Initiating
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 1.1 Project aligned with organizational objectives and customer needs. | [5 empty] | Managing Projects with EPLC
1.1.1 Understands the project alignment | Description of the project alignment | NA |  |  | 0
1.1.2 Achieves agreement on project alignment with project sponsor | Documented agreement with sponsor |  |  | 0 | 0
1.1.3 Establishes key stakeholders' needs and expectations | Documented stakeholders' needs for a project | NA |  |  | 0
1.1.4 Determines product or service characteristics | Documented high-level stakeholder requirements for products and services linked to a project plan used in delivering a project | NA |  |  | 0
Element 1.2 Preliminary scope statement reflects stakeholder needs and expectations. | [5 empty] | Managing Projects with EPLC
1.2.1 Selects and uses a suitable project management methodology or process | Examples of methods used in previous projects and an explanation of why it was chosen |  |  | 0 | 0
1.2.2 Understands the preliminary scope of the project | Preliminary scope statement or equivalent | NA |  |  | 0
1.2.3 Frames high-level project scope ensuring alignment with organization and customer needs and expectations | Documented stakeholders' needs for a project | NA |  |  | 0
Element 1.3 High-level risks, assumptions and constraints are understood. | [5 empty] | Identifying & Managing Risks
1.3.1 Establishes the project's high-level assumptions and constraints | Documented assumptions and constraints | NA |  |  | 0
1.3.2 Identifies, qualifies and quantifies the project's high-level risks | Risk register containing identified, qualified and quantified high-level risks |  |  | 0 | 0
Element 1.4 Stakeholders identified and their needs are understood. | [5 empty] | Managing Projects with EPLC
1.4.1 Identifies project stakeholders | Documented list of stakeholders | NA |  |  | 0
1.4.2 Conducts stakeholder analysis to gain buy-in and identify needs for the project | Documented description of stakeholder needs and objectives Documented stakeholders position and influence |  |  | 0 | 0
1.4.3 Identifies high-level communication requirements | Documented feedback from stakeholders acknowledging their needs were understood Communications management plan Documented high-level communication strategy |  |  | 0 | 0
Element 1.5 Project charter approved. | [5 empty] | Managing Projects with EPLC
1.5.1 Develops a high-level project strategy | Documented high-level project strategy |  |  | 0 | 0
1.5.2 Establishes the project's key milestones and deliverables | Documented milestones and deliverables | NA |  |  | 0
1.5.3 Develops summary budget | Documented order of magnitude effort estimate | NA |  |  | 0
1.5.4 Supports the project charter preparation | Documented resource requirements Documented summary budget Draft project charter documents | NA |  |  | 0
1.5.5 Uses governance process to obtain sponsor approval and commitment | Approved project charter, with governance documentation e.g. business cases, stage gate meeting minutes |  |  | 0 | 0
Scoring: | Initiating a Project Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Planning
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 2.1 Project scope agreed. | [5 empty] | Planning, Scheduling, Control
2.1.1 Defines project deliverables using a work breakdown structure (WBS) | WBS List of alternatives |  |  | 0 | 0
2.1.2 Obtains agreement for the scope defined by the WBS | Documented agreement from project stakeholders | NA |  |  | 0
2.1.3 Implements scope management | Feedback from stakeholders Scope management plan |  |  | 0 | 0
Element 2.2 Project schedule approved. | [5 empty] | Planning, Scheduling, Control
2.2.1 Defines activities and dependencies to deliver approved scope | Project schedule network diagrams WBS dictionary |  |  | 0 | 0
2.2.2 Estimates time for completion of each activity | Documentation of the process used to determine schedule task durations |  |  | 0 | 0
2.2.3 Defines internal and external dependencies | Project schedule with schedule model data | NA |  |  | 0
2.2.4 Schedules the project activities against the resource commitments | Project schedule with schedule model data |  |  | 0 | 0
2.2.5 Obtains approval for the project schedule | Documented sponsor approval of project schedule | NA |  |  | 0
2.2.6 Communicates project schedule with stakeholders | Documented feedback from stakeholders Documented agreement from project stakeholders |  |  | 0 | 0
Element 2.3 Cost budget approval. | [5 empty] | Planning, Scheduling, Control
2.3.1 Estimates costs for each activity | Examples of activity based costing Approved budget with supporting detail |  |  | 0 | 0
2.3.2 Estimates all other project costs | Approved budget with supporting detail |  |  | 0 | 0
2.3.3 Develops the project budget | Approved budget with supporting detail |  |  | 0 | 0
2.3.4 Develops cost management plan | Cost management plan | NA |  |  | 0
2.3.5 Gains approval for the planned project budget | Documented sponsor approval of project budget | NA |  |  | 0
2.3.6 Communicates planned budget to stakeholders | Documented feedback from stakeholders |  |  | 0 | 0
Element 2.4 Project team identified with roles and responsibilities agreed. | [5 empty] | Planning, Scheduling, Control
2.4.1 Identifies specific resources | Staff management plan with roles and responsibilities |  |  | 0 | 0
2.4.2 Defines roles and responsibilities | Documented team members and stakeholder roles and responsibilities Documented team protocols |  |  | 0 | 0
2.4.3 Reaches agreement with the organization for access to suitable resources | Documented formal agreements for resources |  |  | 0 | 0
2.4.4 Plans resource ramp up and team building | Documented activities for team development and resource ramp up Documented team rules |  |  | 0 | 0
Element 2.5 Communication activities agreed. | [5 empty] | Planning, Scheduling, Control
2.5.1 Builds a project communication plan | Communication management plan |  |  | 0 | 0
2.5.2 Selects suitable tools and methods to communicate with identified stakeholders | Templates to support plan e.g. status report, issue log, lessons learned or other organizational process assets. |  |  | 0 | 0
2.5.3 Schedules activities to address the communication plan | Documented feedback from stakeholders |  |  | 0 | 0
Element 2.6 Quality Management process established. | [5 empty] | Project Assurance
2.6.1 Establishes quality standards to be used within the project that aligns with the organizational quality policy | Documentation of the quality standards used |  |  | 0 | 0
2.6.2 Defines processes to be used to deliver the project deliverables | Project quality process documentation | NA |  |  | 0
2.6.3 Establishes project quality metrics for deliverables, processes and project management performance | Documentation of project quality metrics | NA |  |  | 0
2.6.4 Develops a project quality management plan | Approved project quality management plan including quality baseline | NA |  |  | 0
Element 2.7 Risk response plan approved. | [5 empty] | Identifying & Managing Risks
2.7.1 Develops project risk management plan | Approved risk management plan for project |  |  | 0 | 0
2.7.2 Identifies and quantifies major risks | Documented results of risk analysis Risk register |  |  | 0 | 0
2.7.3 Leads/delegates the effort to find response strategies for each identified risk | Risk response plan including nominated risk owners and contingency costs |  |  | 0 | 0
2.7.4 Estimates risk contingency costs | Risk response plan including nominated risk owners and contingency costs |  |  | 0 | 0
2.7.5 Documents risk response plan | Risk response plan including nominated risk owners and contingency costs |  |  | 0 | 0
2.7.6 Assigns risk responsibility | List of risk owners Risk register |  |  | 0 | 0
2.7.7 Gains agreement from key stakeholders for the project risk response plan | Documented feedback from key stakeholders |  |  | 0 | 0
Element 2.8 Integrated change control processes defined. | [5 empty] | Planning, Scheduling, Control
2.8.1 Leads/delegates the effort to establish a change control process | Documented integrated change control process |  |  | 0 | 0
2.8.2 Involves stakeholders in generating change control plan | Documentation of stakeholder involvement in formulating change control plan | NA |  |  | 0
2.8.3 Ensures the use of a change control process and procedures | Minutes of Change Control Board (CCB) meetings | NA |  |  | 0
2.8.4 Communicates with key stakeholders on change control process | Documented feedback from key stakeholders |  |  | 0 | 0
Element 2.9 Procurement plan approved. | [5 empty] | Procurement Practices for PMs
2.9.1 Analyzes material requirements | Project procurement management plan Bills of Material | NA |  |  | 0
2.9.2 Plans purchases and acquisitions | Purchase requests and orders | NA |  |  | 0
2.9.3 Plans external labor procurement | Documentation to support external labor procurement Resource contracts | NA |  |  | 0
2.9.4 Plans contract administration | Procurement management plan | NA |  |  | 0
2.9.5 Obtains plan approval | Sponsor approval of procurement management plan | NA |  |  | 0
Element 2.10 Project plan approved. | [5 empty] | Planning, Scheduling, Control
2.10.1 Reviews organizational process assets | Documented review and/or use of organizational process assets |  |  | 0 | 0
2.10.2 Reviews enterprise environmental factors | Documented review and/or use of enterprise environmental factors |  |  | 0 | 0
2.10.3 Integrates the planning activities into a complete project management plan | Documentation showing how elements of the project management plan integrates |  |  | 0 | 0
2.10.4 Seeks approval of key stakeholders | Project management plan approved by key stakeholders |  |  | 0 | 0
2.10.5 Establishes project baselines | Documented project baselines |  |  | 0 | 0
2.10.6 Communications approved plan to key stakeholders | Documented feedback from stakeholders |  |  | 0 | 0
2.10.7 Conducts kick-off meeting | Agenda/minutes of kick-off meeting |  |  | 0 | 0
Scoring: | Planning a Project Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Executing
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 3.1 Project scope achieved. | [5 empty] | Planning, Scheduling, Control
3.1.1 Verifies task completion as defined in the project plan | Documented feedback from key stakeholders Documented project tracking actions and status Status/milestone reports Formal acceptance documentation confirming tasks completed successfully Project cost reports showing planned versus actual completion and resource utilization |  |  | 0 | 0
3.1.2 Closes identified performance gaps | Documentation of corrective and preventive action |  |  | 0 | 0
3.1.3 Executes risk management plan | Documentation of corrective and preventive action |  |  | 0 | 0
3.1.4 Manages phase transitions | Governance meetings, actions, minutes Feedback from sponsor Formal approvals |  |  | 0 | 0
Element 3.2 Project stakeholders' expectations managed. | [5 empty] | Managing Projects with EPLC
3.2.1 Reviews stakeholder expectations throughout the project to ensure they are being met within the project scope | Documentation of updates to stakeholder analysis Documentation of actions taken to manage stakeholders expectations | NA |  |  | 0
3.2.2 Interacts with stakeholders to ensure support for the project | Minutes of all stakeholder meetings Documentation of actions taken to manage stakeholders expectations Documented feedback from stakeholders | NA |  |  | 0
Element 3.3 Human resources managed. | [5 empty] | Managing Projects with EPLC
3.3.1 Acquires human resources per staff management plan | Staffing lists Labor contracts Statements of work (SOW) for procured labor |  |  | 0 | 0
3.3.2 Build project team | Project organization chart Documented ways of working |  |  | 0 | 0
3.3.3 Develops project team members | Competence gap analysis Development plan for team members | NA |  |  | 0
Element 3.4 Quality managed against plan. | [5 empty] | Project Assurance
3.4.1Executes quality assurance activities | Documented acceptance of project deliverables by key stakeholders Documented change requests |  |  | 0 | 0
3.4.2 Ensures compliance with quality standards and processes | Documented process improvement recommendations Documented updates to planning documents based on variance from plan |  |  | 0 | 0
Element 3.5 Material resources managed. | [5 empty] | Planning, Scheduling, Control
3.5.1 Requests seller information | List of selected sellers Seller responses | NA |  |  | 0
3.5.2 Selects suitable sellers | Contracts, SOWs Purchase orders | NA |  |  | 0
3.5.3 Executes procurement tasks against schedule commitment | Documented availability of material resources | NA |  |  | 0
3.5.4 Acquires internally supplied resources | Documented availability of material resources | NA |  |  | 0
Scoring: | Executing a Project Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Monitoring
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 4.1 Project tracked and status communicated to stakeholders. | [5 empty] | Planning, Scheduling, Control
4.1.1 Executes the process for capturing project information | Project performance reports |  |  | 0 | 0
4.1.2 Communicates status to stakeholders | Minutes of regular meeting or status reports Documented feedback from stakeholders Performance measurements |  |  | 0 | 0
4.1.3 Ensures action plans are put in place to address any variations to plan | Documented corrective and preventive action plan taken to recover variations |  |  | 0 | 0
Element 4.2 Project change is managed. | [5 empty] | Planning, Scheduling, Control
4.2.1 Identifies changes to baseline project plans | Written change requests submitted for action, authorized by the designated approvers Updates to project plan as a result of approved changes |  |  | 0 | 0
4.2.2 Identifies the impact of the changes to the project plan | Documented results of the analysis of the changes | NA |  |  | 0
4.2.3 Follows the change management process to manage and record changes | Records of approved and implemented changes | NA |  |  | 0
4.2.4 Communicates changes to project stakeholders | Documented communications to stakeholders |  |  | 0 | 0
4.2.5 Execute configuration management process | Documented feedback from stakeholders about configuration management and control practices |  |  | 0 | 0
Element 4.3 Quality is monitored and managed. | [5 empty] | Project Assurance
4.3.1 Records acceptance of completed deliverables | Records of completed and signed-off deliverables |  |  | 0 | 0
4.3.2 Collects project and product metrics | Project and product metric reports |  |  | 0 | 0
4.3.3 Monitors deviation from project baselines | Quality defects reports |  |  | 0 | 0
4.3.4 Recommends corrective and preventive actions | Documentation of corrective and preventive actions |  |  | 0 | 0
4.3.5 Facilitates audits | Audit reports Documented suggestions for improvement | NA |  |  | 0
Element 4.4 Risk is monitored and controlled. | [5 empty] | Identifying & Managing Risks
4.4.1 Updates risk response plan | Updated risk register Documentation of results of risk response plan |  |  | 0 | 0
4.4.2 Recognizes when unknown risks occur | Documentation of previously unknown risks that occur Updated risk register |  |  | 0 | 0
4.4.3 Establishes workarounds for previously unknown risks | Documentation of workarounds for previously unknown risks Update risk response plan |  |  | 0 | 0
4.4.4 Recognizes new risk | Updated risk register |  |  | 0 | 0
4.4.5 Reviews risk response strategies | Documented results of risk mitigation reviews | NA |  |  | 0
4.4.6 Facilitates audits | Audit reports Documented suggestions for improvement | NA |  |  | 0
Element 4.5 Project team managed. | [5 empty] | Leadership for the Project Manager
4.5.1 Holds regular team meetings | Minutes of team meetings |  |  | 0 | 0
4.5.2 Conducts team building activities | Documented results of team building activities |  |  | 0 | 0
4.5.3 Monitors team satisfaction | Results of team satisfaction survey | NA |  |  | 0
4.5.4 Provides feedback on team and individual member performance | Documented feedback given on a team member Documentation of team feedback | NA |  |  | 0
Element 4.6 Contracts administered. | [5 empty] | Procurement Practices for PMs
4.5.1 Ensures seller contracts are effectively managed | Feedback from sellers | NA |  |  | 0
4.5.2 Collects seller performance metrics | Seller performance metrics reports | NA |  |  | 0
4.5.3 Ensures sellers are part of the project team culture | Documentation of seller interaction and integration with the team Seller satisfaction survey | NA |  |  | 0
4.5.4 Facilitates audits | Audit reports Documented suggestions for improvement | NA |  |  | 0
Scoring: | Monitoring a Project Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Closing
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 5.1 Project outcomes accepted. | [5 empty] | Managing Projects with EPLC
5.1.1 Obtains final acceptance | Documented approval of project outcome |  |  | 0 | 0
5.1.2 Meets all contractual requirements where required | Documentation of finished and unfinished deliverables Documented acceptance that terms of the contract have been met |  |  | 0 | 0
5.1.3 Transitions all deliverables to operations | Documented acceptance by operations |  |  | 0 | 0
Element 5.2 Project resources released. | [5 empty] | Managing Projects with EPLC
5.2.1 Executes the organizational processes for releasing project resources | Example of a timetable for project team member release schedule from a project as it was closed | NA |  |  | 0
5.2.2 Provides performance feedback to project team members | Documented staff performance feedback | NA |  |  | 0
5.2.3 Provides feedback to the organization regarding team members' performance | Performance evaluation reviewed with the functional managers and stored | NA |  |  | 0
Element 5.3 Stakeholder perceptions measured and analyzed. | [5 empty] | Managing Projects with EPLC
5.3.1 Surveys project stakeholders | Documented feedback from stakeholders |  |  | 0 | 0
5.3.2 Analyzes results of feedback | Documented analysis | NA |  |  | 0
Element 5.4 Project formally closed. | [5 empty] | Managing Projects with EPLC
5.4.1 Executes closure activities for the project | Signed acknowledgement of project products or services delivered and documentation of closing activities |  |  | 0 | 0
5.4.2 Closes all financial activities | Documented feedback from finance department on project status |  |  | 0 | 0
5.4.3 Notifies stakeholders formally of project closure | Document communicating project closure stored in project file | NA |  |  | 0
5.4.4 Closes all project contracts | Contracts closed as required |  |  | 0 | 0
5.4.5 Documents and publishes project learning | Documentation of lessons learned |  |  | 0 | 0
5.4.6 Updates organizational process assets | Archived project documents Documented changes to organizational process assets |  |  | 0 | 0
Scoring: | Closing a Project Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Communicating
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 6.1 Actively listens, understands, and responds to stakeholders. | [5 empty] | Building Project Relationships
6.1.1 Actively listens | Survey results from stakeholders Documented observations from communication Documented feedback on empathy and understanding towards others point of view |  |  | 0 | 0
6.1.2 Understands explicit and implicit content of communication | Documented observations from communication Documented confirmation that messages were received and understood |  |  | 0 | 0
6.1.3 Responds to and acts upon expectations, concerns and issues | Change requests Survey results from stakeholders |  |  | 0 | 0
Element 6.2 Maintains lines of communications. | [5 empty] | Leadership for the Project Manager
6.2.1 Engages stakeholders proactively | Documented confirmation that stakeholders needs have been met proactively |  |  | 0 | 0
6.2.2 Disseminates information effectively | Documentation that the communication was effective through conversation, survey, notes, presentations or observation Documentation of relevant and timely communication shared with appropriate stakeholders |  |  | 0 | 0
6.2.3 Maintains formal and informal communication | Minutes from planned and unplanned meetings, brainstorming sessions, etc. |  |  | 0 | 0
Element 6.3 Ensures quality of information. | [5 empty] | Building Project Relationships
6.3.1 Uses appropriate information sources | Documentation of sources and analysis Documented feedback on the sources | NA |  |  | 0
6.3.2 Provides accurate and factual information | Documents showing that factual information is provided Documented feedback on the accuracy of the information | NA |  |  | 0
6.3.3 Seeks validation of information | Documentation of input from subject matter experts (e.g. interest groups, professional bodies, etc.) Meeting minutes | NA |  |  | 0
Element 6.4 Tailors communication to audience. | [5 empty] | Leadership for the Project Manager
6.4.1 Provides relevant information | Documented feedback from recipient confirming information relevance Demonstrated strong presentation skills |  |  | 0 | 0
6.4.2 Uses suitable communication method for the situation | Preferred communication methods identified in stakeholders' analysis Notes from meetings demonstrating suitability of method selection Feedback from stakeholders regarding suitability of method selection |  |  | 0 | 0
6.4.3 Aligns communication with environment or setting | Documented feedback on: Sensitivity to others' specific communication needs and context Appropriate use of formal, informal verbal, nonverbal, and para-lingual components Minutes from team meetings or presentations Examples of various choices of location, time, participants, and privacy settings |  |  | 0 | 0
Scoring: | Communicating Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Leading
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 7.1 Creates a team environment that promotes high performance. | [5 empty] | Leadership for the Project Manager
7.1.1 Expresses positive expectations of team | Documented feedback from team on: Recognizing abilities of team members Supporting decision making Setting positive expectations |  |  | 0 | 0
7.1.2 Promotes team learning and advocates professional and personal development | Individual development plans Funding for development Documented feedback from project team Documentation of new skills gained by team members |  |  | 0 | 0
7.1.3 Encourages teamwork consistently | Examples of creative actions taken to encourage teamwork, respect for different opinions and personalities Documented feedback on acknowledgement of unique skills and abilities Identified responsibilities of team leaders in giving clear, consistent goals |  |  | 0 | 0
7.1.4 Demands and models high performance | Documented standards for individual performance and quality Documented results of project manager performing to standards Documented feedback that the project manager is acting as a role model Examples of holding project members accountable for their commitments |  |  | 0 | 0
Element 7.2 Builds and maintains effective relationships. | [5 empty] | Building Project Relationships
7.2.1 Confines relationships to work-related matters appropriate to the project and local culture | Documented feedback from project team and stakeholders on project manager maintaining formal working relationship with stakeholders Documented guidelines for formal and informal discussion |  |  | 0 | 0
7.2.2 Builds trust and confidence with stakeholders | Examples of: Acting with integrity in all situations Keeping commitments Providing consistent messages in all situations Supporting team members when confronted with unjustified criticism Maintaining composure Demonstrating fair treatment of partners and sellers |  |  | 0 | 0
7.2.3 Creates an environment that encourages openness, respect and consideration of stakeholders | Feedback from stakeholders on openness of issues analysis and resolution Open door policy (is approachable at all times for project-related matters) Examples of sensitivity and genuine interest in feelings and values of others Documented evidence of fair and fact-based decisions |  |  | 0 | 0
Element 7.3 Motivates and mentors project team members. | [5 empty] | Leadership for the Project Manager
7.3.1 Establishes and communicates to the team the project vision, mission statement, and strategic value | Examples of presentations with clear focus on vision, mission, and strategic value Documented feedback from team regarding awareness of strategic value of the project Examples of rallying support behind the strategy and sharing the strategy with team members |  |  | 0 | 0
7.3.2 Rewards performance according to organization guidelines | Documented rewards and recognition records Examples of plans for success of team members Examples of celebrating individual accomplishments on a frequent basis; assures credit is given to the individual |  |  | 0 | 0
7.3.3 Establishes mentoring relationships for team members' development | Examples of mentoring relationships Examples of being sought out as a mentor for others Documented feedback on mentoring activities Examples of progress on individual development plan |  |  | 0 | 0
Element 7.4 Takes accountability for delivering the project. | [5 empty] | Leadership for the Project Manager
7.4.1 Demonstrates ownership of, accountability for, and commitment to the project | Examples of active involvement with all stakeholders and project team members Examples of quickly addressing possible project hindrances, delays, or risks Reports or meeting notes where the project manager takes the responsibility for project mishaps Examples of taking ownership for adverse project outcomes |  |  | 0 | 0
7.4.2 Aligns personal activities and priorities toward increasing likelihood of achieving project goals | Documented priority planning Lists of prioritized action items Examples of active event management |  |  | 0 | 0
7.4.3 Supports and promotes team's actions and decisions | Documented feedback from project team members that project manager acts assertively on their behalf Meeting notes reflecting project manager's support for team's actions and decisions Keeps abreast of project team activities and maintains accountability for delivery of work Takes a stand in front of higher authorities to support team's project actions as if they were their own |  |  | 0 | 0
Element 7.5 Uses influencing skills when required. | [5 empty] | Leadership for the Project Manager
7.5.1 Applies appropriate influencing technique to each stakeholder | Examples of different styles on different occasions Document describing alternative approaches used to influence Examples of strong facilitation and negotiation skills Example of the ability to educate |  |  | 0 | 0
7.5.2 Uses experts or third parties to persuade others | Examples of using positional power of others to influence Examples of using third party's knowledge power to influence Examples of networking and gathering support for the project while not manipulating for personal gain |  |  | 0 | 0
Scoring: | Leading Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Managing
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 8.1 Builds and maintains the project team. | [5 empty] | Leadership for the Project Manager
8.1.1 Ensures expectations and responsibilities are clear to team members and they understand their importance to the project | Documented feedback from project team on clarity of roles and responsibilities Team correspondence Documented project directives, tasks, and assignments Published Resource Assignment Matrix (RAM) Examples of active participation of each member to team activities |  |  | 0 | 0
8.1.2 Maintains a positive attitude and effective relationships among team members | Examples of effective conflict resolution Documented feedback from team members demonstrating: Respect for others by appealing to reason in project context Genuinely valuing input and expertise of others on the team Willingness to learn from others Examples of team events to facilitate bonding and rapport within the team Celebration of team work and achievements |  |  | 0 | 0
8.1.3 Identifies, evaluates, and selects internal and external talent | Project resource requirements documentation Inventories of suitable team members identified from internal talent pool Predefined selection criteria applied to resources acquisition |  |  | 0 | 0
8.1.4 Promotes healthy work - life balance | Documented feedback from project team members Meeting notes documenting balance issues Documented plan of action to achieve balance Examples of actions taken to improve job efficiency and productivity |  |  | 0 | 0
Element 8.2 Plans and manages for project success in an organized manner. | [5 empty] | Leadership for the Project Manager
8.2.1 Works with others to clearly identify project scope, roles, expectations, and tasks specifications | Documented feedback on level of involvement of others in the planning process |  |  | 0 | 0
8.2.2 Applies organization or industry standards and generally accepted practices to the project | Examples and feedback from the project team, stakeholders and subject mater experts on following industry generally accepted practices Membership in Project Management Institute (PMI), Specific Interest Groups (SIGs), workshops, conferences, or organizations Proposed measures and improvements intended to achieve or exceed industry generally accepted practices Project plan that incorporates industry standards |  |  | 0 | 0
8.2.3 Tailors generally accepted practices for successful completion of the project | Documented change of generally accepted practices Approved changes to project management procedures to accommodate generally accepted practices |  |  | 0 | 0
8.2.4 Organizes project information, emphasizing appropriate levels of detail | Examples of standard methodologies used in project Meeting minutes Project status reports or updates Repository for project artifacts Examples of knowledge management |  |  | 0 | 0
8.2.5 Insists on compliance with processes, procedures, and policies | Monitored compliance of processes, procedures, and policies Examples of enforcing policies and procedures Documented use of performance metrics to manage projects |  |  | 0 | 0
Element 8.3 Resolves conflict involving project team or stakeholders. | [5 empty] | Building Project Relationships
8.3.1 Ensures that the team and stakeholders are fully aware of the team rules | Documented team rules |  |  | 0 | 0
8.3.2 Recognizes conflict | Examples of conflict occurring within the project Team survey results |  |  | 0 | 0
8.3.3 Resolves conflict | Examples of conflict resolution techniques used Feedback from team and stakeholders on satisfactory resolution of conflict |  |  | 0 | 0
Scoring: | Managing Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Cognitive
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 9.1 Takes a holistic view of project. | [5 empty] | PM Foundations
9.1.1 Understands project stakeholders needs, interests, and influences for project success | Stakeholder analysis Communication plan aligned with stakeholders' needs Stakeholders' needs and objectives documented in project charter and project plan |  |  | 0 | 0
9.1.2 Understands how project actions impact other areas of the project, other projects, and organizational environment | Related external events included in project schedule Necessary documentation of project impact on organizational environment, if appropriate |  |  | 0 | 0
9.1.3 Understands both the formal and informal structure of organizations | Documented feedback from stakeholders on use of formal and informal organizational knowledge | NA |  |  | 0
9.1.4 Understands organizational politics | Documented feedback from stakeholders on use of formal and informal organizational politics | NA |  |  | 0
9.1.5 Uses emotional intelligence to understand and explain others' past actions and current attitudes, and anticipate future behavior | Documented feedback on capturing verbal and non-verbal cues of the team Documented feedback from the team that the behaviors displayed are appropriate Documented feedback that different persuasion and motivation techniques were applied appropriate to each individual |  |  | 0 | 0
Element 9.2 Effectively resolves issues and solves problems. | [5 empty] | Building Project Relationships
9.2.1 Simplifies complexities for a complete and accurate analysis | Visual representations of project issues and interdependencies (lists, diagrams, relationship maps etc.) Analysis documents indicating use of techniques to break apart complex problems to find solutions |  |  | 0 | 0
9.2.2 Applies complex concepts or tools when needed | Issues log that provides methods proposed for analysis of complex issues Documented root-cause analysis, portfolio analysis, expert judgment etc. Documented analysis supporting issues resolution |  |  | 0 | 0
9.2.3 Applies lessons learned to resolve current project issues | Documentation of application of lessons learned to current project issues |  |  | 0 | 0
9.2.4 Aggregates multiple related issues to understand the complete picture | Summary reports or project scorecards outlining the relationships and linkages between project issues | NA |  |  | 0
9.2.5 Observes discrepancies, trends, and interrelationships in project data | Requests for information validation or confirmation Documented trend analysis | NA |  |  | 0
Element 9.3 Uses appropriate project management tools and techniques. |  |  |  | 0 | 0 | PM Foundations
9.3.1 Understands PM tools and techniques | List of available tools and/or techniques | NA |  |  | 0
9.3.2 Selects appropriate tools and/or techniques | List of available tools and/or techniques Documented selection process and results | NA |  |  | 0
9.3.3 Applies selected tools and/or techniques to project management | Outcomes achieved through use of tools and/or techniques | NA |  |  | 0
Element 9.4 Seeks opportunities to improve project outcome. | [5 empty] | Leadership for the Project Manager
9.4.1 Provides a framework to address opportunities and concerns | Lists of issues and associated opportunities or concerns distributed to all team members along with a clearly communicated process for updating the list Maintains issues log current and communicates changes/additions in it to all the stakeholders Meeting notes where issues were addressed documenting approaches and solutions identified Comparison between actions proposed and results obtained |  |  | 0 | 0
9.4.2 Looks for opportunities to improve project value or execution | Risk register showing opportunities Notes from brainstorming sessions, meetings, etc. where new opportunities were identified Documented suggestions in projects, or actions taken in a project related to the results obtained |  |  | 0 | 0
9.4.3 Seizes relevant opportunities as they emerge | Meeting notes where opportunities were analyzed Entries in change control process Examples of opportunities related to the moment they are presented during the evolution of the project |  |  | 0 | 0
9.4.4 Consolidates opportunities and passes them to the organization | Emails, meeting notes and other communication artifacts regarding project opportunities Documented proposals to clients or internal stakeholders indicating added value for pursuing identified opportunities Number of opportunities identified and pursued |  |  | 0 | 0
Scoring: | Cognitive Ability Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Effectiveness
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 10.1 Resolves project problems. | [5 empty] | Leadership for the Project Manager
10.1.1 Employs appropriate problem solving techniques | Documented needs analysis (e.g., design inputs list) Documented feedback from stakeholders of problem solving techniques Documented use of proper knowledge management tools Issue log with resolution documentation |  |  | 0 | 0
10.1.2 Validates that proposed solutions resolve the problem and are within the project boundaries | Documented use of proper knowledge management tools Issue log with resolution documentation Documented feedback from stakeholder the problems were solved |  |  | 0 | 0
10.1.3 Chooses solutions that maximize project benefit and minimize negative impacts | Documented feedback from stakeholder stating the problems were resolved Documented impact of solution on project Documented external and/or environmental impact of solution |  |  | 0 | 0
Element 10.2 Maintains project stakeholder involvement, motivation and support. | [5 empty] | Building Project Relationships
10.2.1 Uses stakeholder communication to maintain stakeholder motivation | Communication plan Updates to stakeholder analysis Documented feedback from stakeholders stating that they felt motivated |  |  | 0 | 0
10.2.2 Constantly seeks opportunities to communicate project status and directions to meet the needs and expectations of stakeholders | Examples where the individual took an opportunity to communicate status Documented feedback from stakeholders on how their needs were met |  |  | 0 | 0
10.2.3 Includes experts in meetings and discussions to influence and obtain stakeholder support | Examples of how consensus and support were achieved on different issues Minutes from meetings where subject matter experts were invited for consultations with stakeholders |  |  | 0 | 0
10.2.4 Uses objectivity for consensus building | Documented use of best practices for making team decisions Examples of influencing biased team members toward objective position |  |  | 0 | 0
Element 10.3 Changes at the required pace to meet project needs. | [5 empty] | Leadership for the Project Manager
10.3.1 Adapts to changes in the project environment to minimize adverse project impacts | Documented feedback from stakeholders stating that the individual displayed a "can-do" attitude despite changes Documented risk mitigation activities |  |  | 0 | 0
10.3.2 Demonstrates flexibility towards changes that benefit the project | Risk registry updates identifying new opportunities Documented opportunities analysis Change requests |  |  | 0 | 0
10.3.3 Takes positive actions to capitalize on opportunities or to resolve present problems | Documented feedback from stakeholders that the project manager demonstrated an action-oriented and proactive approach Examples where the project manager resolved outstanding problems Project library with relevant documentation of technologies, techniques, or methods used during the project execution |  |  | 0 | 0
10.3.4 Enables a change-friendly environment by fostering continuous learning | Documented training recommendations for team members Project schedule includes time for team members to study new solutions, situations, or technologies Project library with relevant documentation of technologies, techniques, or methods used during the project execution |  |  | 0 | 0
10.3.5 Acts as a change agent | Documented feedback from stakeholders regarding changes initiated or facilitated by project manager Documented feedback from stakeholders stating that the project manager demonstrated positive self-esteem and self-confidence |  |  | 0 | 0
Element 10.4 Uses assertiveness when necessary. | [5 empty] | Leadership for the Project Manager
10.4.1 Takes initiative when required, assuming calculated risks to expedite project delivery | Feedback from stakeholders the PM took initiative when required Issue log with documented resolutions Issue escalation reports showing timely decision path |  |  | 0 | 0
10.4.2 Prevents inconclusive discussion, makes a decision, and takes appropriate action | Feedback from team on actions taken Examples where the PM declined a proposal without causing an argument and maintained cooperation Examples where the PM resolved a crisis by assessing the situation and offering decisive action |  |  | 0 | 0
10.4.3 Shows persistence and consistency in actions | Documented feedback from stakeholders stating that the PM showed persistence and consistency Meeting minutes, action item notes, or status reports showing decisions made Examples of maintaining motivation when faced with challenges |  |  | 0 | 0
10.4.4 Makes timely decisions based on facts while managing ambiguity | Decision memoranda or decision analysis documents demonstrating factual analysis of issues and prompt decision-making Issue log showing time from recording to resolution Issues escalation reports showing timely decision path |  |  | 0 | 0
Scoring: | Effectiveness Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Professionalism
Performance Criteria | Types of Evidence | Self Assessment | Reviewer |  |  | Primary Course to fulfill
Element 11.1 Demonstrates commitment to the project. | [5 empty] | Leadership for the Project Manager
11.1.1 Understands and actively supports the project's and organization's mission and goals | Documented alignment of project goals and objective with organization's missions and strategy Examples where support was given when project goals differ from personal preferences Examples of defined project activities that support organizational goals |  |  | 0 | 0
11.1.2 Cooperates with all stakeholders to achieve project objectives | Examples of specific cooperative efforts to achieve project objectives Examples where team-building techniques were used to foster cooperation |  |  | 0 | 0
11.1.3 Makes sacrifices where necessary to move project forward | Examples of prior options taken for effective project execution while giving personal benefits a lower priority Examples where the PM demonstrated positive attitude while dealing with project challenges |  |  | 0 | 0
Element 11.2 Operates with integrity. | [5 empty] | Leadership for the Project Manager
11.2.1 Adheres to all legal requirements | Feedback from stakeholders all legal requirements were met Documented log of legal requirements applied to the project with written stakeholder approval |  |  | 0 | 0
11.2.2 Works with a recognized set of ethical standards | Documented feedback from stakeholders stating that PM modeled ethical standards were used Documented feedback from stakeholders indicating the PM neither offered or accepted inappropriate payments or other items from any stakeholders |  |  | 0 | 0
11.2.3 Seeks to avoid and discloses any possible conflict of interests to all stakeholders | Example of truthful reporting of potential conflict of interests Organizational Conflict of Interest (OCI) statement and OCI plan |  |  | 0 | 0
11.2.4 Maintains and respects confidentiality of sensitive information | Documented feedback from stakeholders the individual maintains confidentiality Examples of project documentation that include the confidentiality or security level classification notice |  |  | 0 | 0
11.2.5 Respects the intellectual property of others | Documented agreements for reuse of protected intellectual property Documented searches for potentially applicable patents, trademarks, or copyrights Examples of copyright notice with source indication whenever protected intellectual property was used |  |  | 0 | 0
Element 11.3 Handles personal and team adversity in a suitable manner. | [5 empty] | Building Project Relationships
11.3.1 Maintains self-control in all situations and responds calmly | Examples where the PM felt strong emotions (such as anger or extreme frustration) but controlled them Uses stress-management techniques to control response, prevent burnout, and deal with ongoing stress Documented feedback from stakeholders indicating that the individual displayed self control |  |  | 0 | 0
11.3.2 Admits shortcomings and explicitly accepts responsibility for failures | Documented feedback from stakeholders where the individual actively listened to constructive feedback and acted on it Examples where the individual accepted responsibility for failure |  |  | 0 | 0
11.3.3 Learns from mistakes to improve future performance | Documented lessons learned Documented feedback from stakeholders stating that the individual learned from mistakes Examples where the individual analyzed his or her own performance to understand causes of mistakes and failures |  |  | 0 | 0
Element 11.4 Manages a diverse workforce. | [5 empty] | Leadership for the Project Manager
11.4.1 Develops elements of trust and respect within the project environment | Documented feedback from team that the PM displayed an awareness of, respect for, and willingness to accommodate cultural differences Examples where the team celebrated achievements |  |  | 0 | 0
11.4.2 Ensures team's adherence to cultural issues, legal requirements, and ethical values | Document describing ethical standards and stakeholders' value systems Examples of consistently good moral judgment and behavior Documented analysis of applicable legislation, standards, and local customs relevant to the project |  |  | 0 | 0
11.4.3 Respects personal, ethnic, and cultural differences | Documented feedback from the team the PM respected personal, ethnic and cultural differences Examples of where the PM valued the contribution of each team member |  |  | 0 | 0
11.4.4 Creates an environment of confidence and respect for individual differences | Documented feedback from team showing that they had confidence that the PM respected individual differences Examples where the PM created the conditions that motivated and enabled others to contribute their best |  |  | 0 | 0
Element 11.5 Resolves individual and organizational issues with objectivity. | [5 empty] | Leadership for the Project Manager
11.5.1 Respects the organizational framework for running projects | Documented feedback from stakeholders that the individual respected privileges set forth for project managers in the organization Documented feedback from stakeholders that the project manager follows rules of collaboration and reporting within programs or portfolios of projects |  |  | 0 | 0
11.5.2 Balances individual interest with organizational interest | Documented feedback from stakeholders that the individual saw clear distinctions between individual and organizational interests Documented feedback from stakeholders that the individual adhered to PMI's professional code of conduct |  |  | 0 | 0
11.5.3 Assigns team members in an unbiased way to appropriate tasks | Skills assessment documentation indicating each team member's strength and weaknesses Responsibility Assignment Matrix (RAM) aligned with the team member's skills assessment Examples of personnel assignment that allows them to grow by doing more than status quo |  |  | 0 | 0
Scoring: | Effectiveness Competency Score: |  |  | 0 | 0
Below Expectations = 0 (Avg <2.5) |  | NA | NA
Meets Expectations = 3 (Avg >=2.5 and <4.5)
Exceeds Expectations = 5 (Avg >=4.5)

## Totals
Performance | Self | Reviewer
Initiating
Planning
Executing
Monitoring and Controlling
Closing
Performance Score: | #DIV/0! | #DIV/0!
| #DIV/0! | #DIV/0!
Personal | Self | Reviewer
Communicating
Leading
Managing
Cognitive Ability
Effectiveness
Professionalism
Personal Score: | #DIV/0! | #DIV/0!
| #DIV/0! | #DIV/0!
Knowledge Score: | 3 | 2.5
| Meets Expectations | Meets Expectations

## DataValues
Exceeds | PM Foundations
Meets | Planning, Scheduling, Control
Below | Identifying & Managing Risks
NA | Recovering Failing Projects
Project Assurance
Managing Project Requirements
Successful Project Meetings
Managing Organizational Change
Leadership for the Project Manager
Building Project Relationships
Procurement Practices for PMs
Managing Projects with EPLC
MS Project I
MS Project II
PMP Exam Prep Course